Wisconsin State Elections Board

SVRS Contract #EB-SVRS1

Exhibit A – Payment Schedule

11/12/04

TABLE OF CONTENTS

- Payment Schedule 	3

- Costs	…4

2.1  Base Costs	4

2.2  SVRS Software Customizations	4

2.3  Customization Costs for Priority 3 and 4 Options	5

2.4  Additional Customization Costs	5

2.5  Total Implementation	6

- Software Maintenance and Support	…6

3.1  Software Maintenance and Level 1 and Level 2 Support Costs	6

3.2  Hourly Billing Rates	7

# Payment Schedule

| Payment | Project Milestone | Amount |
| --- | --- | --- |
| I | Implementation Planning Deliverables | $650,100.66 |
| II | SVRS Release 1 Specifications | $650,100.66 |
| III | SVRS Release 1 CRP & Configuration Design | $650,100.66 |
| IV | SVRS Release 2 Specifications | $650,100.66 |
| V | SVRS Release 2 CRP & Configuration Design | $650,100.66 |
| VI | SVRS Release 1 Integration & System Test | $650,100.66 |
| VII | SVRS Release 1 Delivery for User Testing | $1,300,201.40 |
| VIII | SVRS Release 1 Acceptance Test | $650,100.66 |
| IX | SVRS Release 1 Pilot Implementation | $650,100.66 |
| X | SVRS Data Conversion | $650,100.66 |
| XI | SVRS Release 1 Implementation Final Acceptance and SVRS Release 2 Delivery | $650,100.66 |
| XII | Holdback Payment #1 – January 2006 | $243,787.75 |
| XIII | Holdback Payment #2 – February 2006 | $243,787.75 |
| XIV | Holdback Payment #3 – April 2006 SVRS Release 2 Final Acceptance and Project Closeout | $487,575.50 |
| XV | Holdback Payment #4 – May 2006 | $243,787.75 |
| XVI | Holdback Payment #5 – June 2006 | $243,787.75 |
| XVII | Final Holdback Payment – January 2007 or at the End of Warranty Period | $487,575.50 |
|  | Total | $9,751,510 |

# Costs

## Base Costs

| Total Software (Fixed Cost) | $1,500,000 |
| --- | --- |

## SVRS Software Customizations (Fixed Cost)

| Item # | Customization Description for Priority 1 and 2 | Requirement # | Cost |
| --- | --- | --- | --- |
| 1 | - For voter public access, the system shall have multi-lingual capabilities for two different languages. | B-37 | $9,280 |
| 2 | The system shall provide multi-level totaling for ad hoc query functionality | B-109 | $25,984 |
| 3 | The system shall integrate with ballot creation software systems by creation of an interface to two (2) different types of ballot creation software. | B-357 | $46,400 |
| 4 | The system shall allow for Web-enabled filing of the Campaign Registration Statement (form EB-1) data | B-488 | $157,760 |
| 5 | The system shall record and maintain identification of canvas as original or recount in canvass information | B-554 | $48,720 |
| 6 | The system shall generate a report detailing the results (number of votes and percentage of total) of the election for Canvass Reporting Unit Detail – Recount | B-560 | Included with the cost of B-554 |
| 7 | The system shall allow an authorized user to override the automatic assignment of voters to a polling place with a new custom field added to store the alternate polling place, a separate custom ‘exception’ poll list (for those voters in a polling place who have been assigned to that polling place as an alternative to their default polling place), and a custom correspondence to the voter | B-194 | $32,480 |
| 8 | The system shall record and maintain the hours of the polling place operation by the addition of a new field for the polling place to allow the entry of hours of operation for each polling location. | B-392 | $18,560 |
| 9 | The system shall allow the user to assign wards to the reporting unit by providing new screens and processes added to assign election polling places to a reporting unit and to allow the entry of canvassed results by reporting unit. In addition, the election plan wizard will be modified to include the reporting units. | B-323 | $182,700 |
| 10 | The system shall record and maintain the reporting unit in which votes were received in canvass information | B-552 | Included with the cost of B-323 |
|  | Total for Priority 1 and 2 Customizations |  | $521,884 |

## Customization Costs for Priority 3 and 4 Options (Fixed Cost)

| Item # | Customization Description for Priority 3 | Requirement # | Cost |
| --- | --- | --- | --- |
| 11 | Does the system allow an authorized user to enter non-participation in an election (as a way of more efficiently recording voters who did participate)? | B-362 | $27,840 |
| 12 | Does the system allow for Web-enabled, read-only access to Election Results data? | B-571 | -included-1 |
|  | Total cost of customizations for priority 3 options. |  | $27,840 |

| Item # | Customization Description for Priority 4 | Requirement # | Cost |
| --- | --- | --- | --- |
| 13 | Does the system have the ability to identify electors who are eligible for jury selection? | B-207 | -included-1 |
| 14 | Does the system record and maintain the elector’s history of jury participation? | B-208 | -included-1 |
|  | Total cost of customizations for priority 4 options. |  | 0 |

- These requirements will be included in the second release of AESM 2004, which are currently planned to be available in the second quarter of 2005.

## Additional Customization Costs (Fixed Cost)

| Item # | Customization Description | Requirement # | Cost |
| --- | --- | --- | --- |
| 15 | The system shall accept electronic canvassing results with the creation of an interface to accept electronic canvassing results in two (2) different formats. | New | $46,400 |
| 16 | Customization to search on WSEB number | New | $16,440 |
| 17 | Customization to search on HINDI number | New | $16,440 |
| 18 | Provide a web portal for counties to submit their electronic files for data conversion. | New | $12,000 |
| 19 | The system shall accept voting age population and total population Census data by municipality via an interface. | New | $11, 600 |
|  | Total Additional Customization Costs |  | $102,880 |

| Total Customization Costs | $652,604 |
| --- | --- |

## Total Implementation (Fixed Cost)

| Service | Cost |
| --- | --- |
| Software Implementation Cost | $6,818,906 |
| Splitting SVRS into two (2) releases Cost | $690,000 |
| 3 Month of Additional Warranty | $90,000 |
| Total Implementation Cost | $7,598,906 |

# Software Maintenance and Support

## The following not-to-exceed costs are only paid if the SEB purchases one or more of the services.

| Cost | 7/1/05 6/30/06 | 7/1/06 6/30/07 | 7/1/07 6/30/08 | 7/1/08 6/30/09 | 7/1/09 6/30/10 |
| --- | --- | --- | --- | --- | --- |
| Software Maintenance | N/A | $175,000* | $375,000 | $400,000 | $425,000 |
| Level 1 Support | $425,000 | $275,000 | $150,000 | $200,000 | $160,000 |
| Level 2 Support | $400,000 | $450,000 | $250,000 | $250,000 | $215,000 |
| - Total | $825,000 | $900,000 | $775,000 | $850,000 | $800,000 |
| - Grand Total 70-months | $4,150,000 |  |  |  |  |

*For the period 1/1/07 to 6/30/07.

|  | Hours |
| --- | --- |
| The number of hours provided for fixes/modifications in the maintenance contract as described above. | 4,000 (1,000 per year) |

## Hourly billing rates for the software modification personnel per staff level.

| Staff Level | Billing Rate | Qualification/Experience Specifications for Each Billing Rate |
| --- | --- | --- |
| Manager/Project Director | $200 -$330 | Low: At least 8 years of experience in information systems implementation, change management efforts or business process redesign. The person would be qualified to perform the following tasks: - Plan and manage the work of information systems project teams - Conceptual design and development of training curricula - Lead clients through streamlining, reengineering and transforming business processes - Manage client contracts. High: At least 10 years of experience in information systems implementation, change management efforts or business process redesign. The person would be qualified to perform the following tasks: - Design and implement new organization structures - Conceptual design and development of training curricula - Work with client executives to facilitate organizational change programs and realize business goals - Ensure consistency of quality across multiple projects - Manage client contracts. |
| Functional/Technical Lead | $100-$85 | Low: At least 3 years of experience in information systems implementation, change management efforts or business process redesign. The person would be qualified to perform the following tasks: - Develop functional and technical information system designs. - Supervise business integration analysts in the development of software designs, computer programming, system testing or training curricula - Define information systems requirements High: At least 5 years of experience in information systems implementation, change management efforts or business process redesign. The person would be qualified to perform the following tasks: - Plan and manage the work of information systems project teams - Lead clients through streamlining, reengineering and transforming business processes - Develop and execute project budgets. |
| Analysts | $80-$150 | Low: At least 1 year of experience in information systems implementation, change management efforts or business process redesign. The person would be qualified to perform the following tasks: - Design, code and test functional components of information systems according to project specifications - Identify and document functional requirements for information systems - Develop project documentation and user training materials according to program specifications - Provide technical support to software development teams High: At least 2 years of experience in information systems implementation, change management efforts or business process redesign. The person would be qualified to perform the following tasks: - Design, code and test functional components of information systems according to project specifications - Identify and document functional requirements for information systems - Develop project documentation and user training materials according to program specifications - Provide technical support to software development teams |
| Programmer/Analysts | $75 - $125 | Low: At least 1 year of experience in information systems implementation, change management efforts or business process redesign. The person would be qualified to perform the following tasks: - Design, code and test functional components of information systems according to project specifications - Identify and document functional requirements for information systems - Develop project documentation and user training materials according to program specifications - Provide technical support to software development teams High: At least 2 years of experience in information systems implementation, change management efforts or business process redesign. The person would be qualified to perform the following tasks: - Design, code and test functional components of information systems according to project specifications - Identify and document functional requirements for information systems - Develop project documentation and user training materials according to program specifications - Provide technical support to software development teams |
| Trainers | $95 - $170 | Low: At least 1 year of experience in information systems implementation, change management efforts or business process redesign. The person would be qualified to perform the following tasks: - Create Training Content - Data Creation - Environment Setup - Logistics Execution High: At least 3 years of experience in information systems implementation, change management efforts or business process redesign. The person would be qualified to perform the following tasks: - Training Execution - Instructional Design - Logistics Management - Audience Analysis - Training Design |
| Hardware/Network Technician | $90 - $110 | Low: Has been trained on how to complete pc or network installation\configuration tasks. These people are either hold a professional certification or in the process of obtaining one High: At least 1 year of experience in completing pc or network installation\configuration tasks. These people will usually hold a professional certification. |

Billing Rate Assumptions:

- Billing rates are current as of proposal submission and are valid through August 31, 2005.

- Billing rates include travel expenses.

Note:  This Exhibit A may only be changed by Contract Amendment.