Wisconsin State Elections Board

SVRS Contract #EB-SVRS1

Exhibit B – Statement of Work

11/12/04

Table of Contents

Exhibit B - SVRS Statement of Work

1.0	Purpose	1

2.0	Contractor Key Personnel	1

2.1	Availability	1

2.2	Key Personnel Responsibilities	1

3.0	SVRS Project Milestones	2

3.1	Delivery Dates	2

4.0	Deliverables	2

4.1	Milestone I : Implementation Planning Deliverables	3

4.2	Milestone II:  SVRS Release 1 Specifications	4

4.3	Milestone III: SVRS Release 1 CRP & Configuration Design	4

4.4	Milestone IV: SVRS Release 2 Specifications	6

4.5	Milestone V: SVRS Release 2 CRP & Configuration Design	7

4.6	Milestone VI: SVRS Release 1 Integration & System Test	7

4.7	Milestone VII: SVRS Release 1 Delivery	8

4.8	Milestone VIII: SVRS Release 1 Acceptance Test	8

4.9	Milestone IX: SVRS Release 1 Pilot Implementation	9

4.10	Milestone X: SVRS Data Conversion	9

4.11	Milestone XI: SVRS Release 1 Implementation and SVRS Release 2 Delivery	10

4.12	Milestone XII: SVRS Final Acceptance & Project Closeout (Holdback Payment #3)	10

4.13	Deliverable Dates and Review Periods	11

5.0	Documentation	12

6.0	Hardware and Third Party Software	13

7.0	SEB Responsibilities	13

Exhibit B – Statement of Work

# Purpose

The Statement of Work (SOW) is issued under and subject to the Contract between the State Elections Board (SEB), acting on behalf of the State of Wisconsin, and the Contractor for a Statewide Voter Registration System (SVRS).  This SOW outlines the scope of work to be completed in successfully implementing the SVRS. Unless otherwise provided in this Exhibit B – Statement of Work (SOW), capitalized terms used have the meaning specified in the Contract.

# Contractor Key Personnel

## Availability

The Contractor’s Key Personnel shall be primarily located on site at the SEB in Madison, Wisconsin.

|  |  | Table 1 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | SVRS Implementation Phases |  |  |  |  |  |  |  |  |
| Named Resource | Project Role | Planning | Analysis | Design | Configuration Development | system Test | Acceptance Test | Pilot Implementation | Statewode Implementation | Final Acceptance |
| John M. Fyfe | Project Director | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% |
| Bryan Klimczak | Project Manager | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |
| Dennis Ramos | Technical Team Lead | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |
| Alicia Kinsey | Functional Team Lead | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |
| Josh Murray | Transition Team Lead | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |

## Key Personnel Responsibilities

The following are responsibilities of the Key Personnel.  The Contractor’s Key Personnel are not limited to the responsibilities identified in the chart below.

|  |  | Table 2 |  |
| --- | --- | --- | --- |
|  |  | SVRS Implementation Responsibilities |  |
| John M. Fyfe | Project Director | - Program Management - Issue and Risk Escalation | - Contractor Resource Management - Client Satisfaction |
| Bryan Klimczak | Project Manager | - Project Management - Issue and Risk Management - Contract Administrator | - Direction of Day to Day Project Tasks - Overall Project Status Consolidation and Reporting |
| Dennis Ramos | Technical Team Lead | - Infrastructure Installation and Configuration - Security | - Liaison with DET - Technical Knowledge Transfer |
| Alicia Kinsey | Functional Team Lead | - Application Requirement and Configuration | - Interfaces |
| Josh Murray | Transition Team Lead | - Communication Planning - Communication with Stakeholders | - Training - Data Conversion and Population |

# SVRS Project Milestones

## Delivery Dates

The Milestones represent key project checkpoints defined by the completion of a series of Deliverables.  A Milestone is considered complete once all the associated Deliverables have been accepted by SEB.  Associated Deliverables to each Milestone are found in Section 4.0. For the purpose of this document, the Contractor estimates the dates it expects the Milestones to be delivered to the SEB.

| Table 3 |  |  |
| --- | --- | --- |
|  | Project Milestone | Estimated Delivery Date |
| I | Implementation Planning Deliverables | 12/15/04 |
| II | SVRS Release 1 Specifications | 1/14/05 |
| III | SVRS Release 1 CRP & Configuration Design | 2/15/05 |
| IV | SVRS Release 2 Specifications | 3/15/05 |
| V | SVRS Release 2 CRP & Configuration Design | 4/15/05 |
| VI | SVRS Release 1 Integration & System Test | 5/16/05 |
| VII | SVRS Release 1 Delivery for User Testing | 6/17/05 |
| VIII | SVRS Release 1 Acceptance Test | 7/15/05 |
| IX | SVRS Release 1 Pilot Implementation | 8/17/05 |
| X | SVRS Data Conversion | 9/16/05 |
| XI | SVRS Release 1 Implementation Final Acceptance & SVRS Release 2 Delivery | 10/28/05 |
| XII | SVRS Release 2 Final Acceptance & Project Closeout (Holdback Payment #3) | 3/17/06 |

# Deliverables

During the development, review, and signoff procedures for each Deliverable:

      - The Contractor shall document overall project development standards and templates.

      - The Contractor shall work with the SEB to create a Deliverable Expectation Document (DED) that outlines what will be included in the Deliverable.

      - Once SEB and Contractor agree on the DED, the Contractor shall commence with the Deliverable creation.

      - The Contractor shall submit individual components of the Deliverable in draft form to the SEB for review and return with comments to Contractor.

      - Once the Deliverable is completed, Contractor will certify it as such and submit it to the SEB for approval.

      - SEB will review the Deliverable per the Acceptance Testing process per the Contract.

      - Contractor and SEB will participate jointly in regular planning and status meetings to coordinate the timing and level of SEB, DET and other State agencies participation in development of deliverables.

## Milestone I: Implementation Planning Deliverables

This Milestone is considered complete once the associated deliverables have been accepted by the SEB.

| Table 4 |  |  |
| --- | --- | --- |
| ID | Deliverable | Description |
| IP1 | Implementation Plan | The Implementation Plan sets forth the overall plan for how the project shall be performed, including schedule, staffing, and quality assurance. The Implementation Plan shall be a living document. This document shall consist of the following but is not limited to: - Project Schedule For Each Milestone - Project Work Plan - Project Resource Plan - Project Quality Action Plan - Team Organization Chart - Project Risk Mitigation Plan - Roles & Responsibilities Matrix - Measurement Plan - Change Control Plan - Configuration Management Plan - Risk Management Plan - Decision Document Template and associated process - Issue Management Plan - Quality Management Plan - Staffing Plan - Transition Approach |
| CP1 | Communication Plan | The Project Communication Plan helps guide the project’s communication efforts. The purpose of this plan is to share timely information with affected parties and gather their valued input and experience. This document shall consist of the following but is not limited to: - List and description of project members - Corresponding communication strategies for each member - The key messages each member should receive - The communication development, review, State approval and delivery process - The targets, timelines and methods for delivering the messages - Roles and responsibilities of Contractor and SEB |
| PI1 | Project Initiation | The Project Initiation describes the activities required to setup, train, and prepare the project team for initiating the project. This activity document shall consist of the following but is not limited to: - Workspace and infrastructure setup - Project methodology & tools training - Project reporting training - AESM overview training for SEB project team - Project Orientation Plan |

## Milestone II:  SVRS Release 1 Specifications

This Milestone is considered complete once the associated Deliverables have been Accepted by the SEB.

| Table 5 |  |  |
| --- | --- | --- |
| ID | Deliverable | Description |
| AAC2 | Application Acceptance Criteria – Release 1 | The Application Acceptance Criteria documents the specific and measurable criteria to be evaluated for acceptance testing purposes. SEB may use this document as a checklist. This Deliverable shall be updated if changes occur. |
| IS2 | Interface Strategy | The Interface Strategy document describes the interface strategy for integrating the SVRS with other systems. This document shall consist of but is not limited to: - Identification of data that needs to be interfaced - Location of where the data is taken from or sent to - Method of how data shall be extracted or imported - A diagram reflecting the interfaces with each external entity including other state agencies - Method for testing each interface |
| BR2 | Requirements Traceability Matrix – Release 1 | The Requirements Traceability Matrix document lists all of the Business Requirements from Exhibit C in the Contract and any additional requirements. It specifies the Release version that the Requirement will be met and is used to validate that the Requirements are complete and correct, that every Requirement item is addressed by some components of the SVRS Application, and that every Application component is built to support some Requirement items. This document will also note if the Requirement is met through a customization or by the AESM software. If the Requirement is met by the AESM software, the document will describe how the software meets this Requirement. If the Requirement is not met by the AESM software, the document will reference the Design Specification that meets the Requirement. This Specification will be used in later phases of the project to track how these Requirements are designed, developed and implemented. |

## Milestone III: SVRS Release 1 CRP & Configuration Design

This Milestone is considered complete once the associated Deliverables have been Accepted by the SEB.

| Table 6 |  |  |
| --- | --- | --- |
| ID | Deliverable | Description |
| SAD3 | Solution Architecture Design | The Solution Architecture Design describes the system hardware and software requirements and develops a technical architecture design for SVRS. This document shall consist of but is not limited to - A diagram reflecting the physical connectivity of the DET SVRS servers and network components - A high-level diagram depicting the new SVRS equipment in the context of the existing State infrastructure - A diagram reflecting the software required to be installed on the DET SVRS servers - Design of the high availability approach for each tier of the SVRS technical architecture including failover and load balance capabilities - The minimum requirements for workstations and peripherals to access the SVRS at the prescribed performance levels - The minimum requirements for the Municipal, County, and State networks allowing the workstations to access the SVRS at the prescribed performance levels - Design of connectivity configuration - SVRS Security Plan - System and data backup design - Environment requirement specifications and strategy - Environment Hardware Specification - Shared Hardware Specification - SVRS and Third Party Software Specification |
| TA3 | Technical Training Assessment | The Technical Training Assessment describes the approach and preliminary assessment for providing Training of the SVRS. This document shall consist of but is not limited to: - A description of the Training approach and the responsibilities of the DET and SEB team members as well as the Contractor - A description of the Training schedule - A list of technical training options to build DET technical skills for SVRS maintenance (vendor, instructor-led, or computer-based training) |
| HDP3 | Help Desk Plan | The Help Desk Plan describes roles and responsibilities of the various participating organizations during the resolution of Help Desk calls. The Plan also describes the escalation process and transfer of the Help Desk calls from Level 1 to the various Level 2 organizations. |
| TP3 | Training Plan | The Training Plan Deliverable includes the approach, schedule, and logistics plan for training the trainers and a high-level approach for training end users. This document shall consist of but is not limited to: - A description of the train-the-trainer approach and the responsibilities of SEB - A listing and description of delivered training with indicator showing the training modules to be updated for SVRS - A definition of the training scope, audience, objectives, approach, and development timelines - A training and onsite support schedule for trainers based on the logical sequence of how the content should be delivered, availability of the participants and deployment timing, and training locations |
| WCP3 | Workstation Installation Checklist | The Workstation Installation Checklist describes how local workstations shall be setup to meet SVRS Requirements and Specifications. |
| CDE3 | Configuration Design – Release 1 | The Configuration Design describes how the SVRS software and custom developed reports, and screens are unit and integration tested. This document shall consist of but is not limited to: - An inventory of the custom developed reports and screens - Configuration Matrix which includes all AESM configuration parameters and initial settings - Detail design for custom reports and screens - A list of requirements that are being satisfied by the design |
| ID3 | Interface Design | The Interface Design describes how the SVRS custom interfaces are developed and tested. This document shall consist of but is not limited to: - An inventory of the custom developed interfaces - Detail design for each custom interface - A list of requirements that are being satisfied by the design |
| DCS3 | Data Conversion Strategy and Approach | The Data Conversion Strategy and Approach document describes the Conversion Strategy and Approach for those municipalities and counties which currently have electronic voter registration records. This document shall consist of but is not limited to: - Identification of data that shall need to be converted - The method of how data shall be cleansed - The method for inputting data into the SVRS - A description of the conversion process - A conversion schedule, including the timeline for mock conversions - A description of the pre-conversion tasks - A description of the process of extracting, cleansing, and loading of the data - A description of known issues and challenges that should be resolved prior to mock conversion - A contingency plan itemizing the risks and mitigation strategies specifically related to conversion activities - Roles and responsibilities of SEB and the Contractor - A mapping of source data to target data including default values and translation rules and calculations applied per municipality and county - A description of validation tests and techniques - A description of validation reports to be produced by Contractor during conversion |

## Milestone IV: SVRS Release 2 Specifications

This Milestone is considered complete once the associated Deliverables have been Accepted by the SEB.

| Table 7 |  |  |
| --- | --- | --- |
| ID | Deliverable | Description |
| AAC4 | Application Acceptance Criteria – Release 2 | The Application Acceptance Criteria documents the specific and measurable criteria to be evaluated for Acceptance Testing purposes. SEB may use this document as a checklist. This Deliverable shall be updated if changes occur. |
| BR4 | Requirements Traceability Matrix – Release 2 | The Requirements Traceability Matrix document lists all of the Business Requirements from Exhibit C in the Contract and any additional requirements. It specifies the Release version that the Requirement will be met and is used to validate that the Requirements are complete and correct, that every Requirement item is addressed by some components of the Application, and that every Application component is built to support some Requirement items. This document will also note if the Requirement is met through a customization or by the AESM software. If the Requirement is met by the AESM software, the document will describe how the software meets this Requirement. If the Requirement is not met by the AESM software, the document will reference the Design Specification that meets the Requirement. This Specification will be used in later phases of the project to track how these Requirements are designed, developed and implemented. |
| TD4 | SVRS Training Design | The SVRS Training Design describes the training approach for the SVRS. The training design shall also be updated and kept updated as changes to the SVRS occur. This document shall consist of but is not limited to: - Online help/training - Detailed Training Requirements - Instructional Design - Design / tailor practice scenarios for End-User Training and Practice Period |

## Milestone V: SVRS Release 2 CRP & Configuration Design

This Milestone is considered complete once the associated Deliverables have been Accepted by the SEB.

| Table 8 |  |  |
| --- | --- | --- |
| ID | Deliverable | Description |
| CDE5 | Configuration Design – Release 2 | The Configuration Design describes how the SVRS software and custom developed reports, and screens are unit and integration tested. This document shall consist of but is not limited to: - An inventory of the custom developed reports and screens - Configuration Matrix which includes all AESM configuration parameters and initial settings - Detail design for custom reports and screens - A list of Requirements that are being satisfied by the design |

## Milestone VI: SVRS Release 1 Integration & System Test

This Milestone is considered complete once the associated Deliverables have been Accepted by the SEB.

| Table 9 |  |  |
| --- | --- | --- |
| ID | Deliverable | Description |
| STP6 | System Test Plan | The System Test Plan describes the overall plan and approach the Contractor shall use to test the SVRS. This document shall consist of but is not limited to: - An overview of the test approach and test scenarios - Verification and validation techniques - A description of the processes employed to control the test effort - A test schedule - A list of the testing tools employed - Roles and Responsibilities |
| STM6 | SVRS Train-the-Trainer Materials | The SVRS Training Materials consist of all materials required to train users in the use of the SVRS. This document shall consist of but is not limited to: - AESM/SVRS End User Manual - AESM/SVRS Instructor Guide - Training procedures / scenarios - Sample Training Schedule - Training materials on training techniques - Updated Online Help – User Guides |
| IC6 | Installation Certification | The Installation Certification shall provide detailed results and issues found during the Certification of the DET Hardware, Software, and Network installation. This document shall consist of but is not limited to: - Hardware results, issues, and resolutions - Software results, issues, and resolutions - Network and Connectivity results, issues, and resolutions |

## Milestone VII: SVRS Release 1 Delivery for User Testing

This Milestone is considered complete once the associated Deliverables have been Accepted by the SEB.

| Table 10 |  |  |
| --- | --- | --- |
| ID | Deliverable | Description |
| STR7 | System Test Results – Release 1 | The System Test Results shall provide the results of the SVRS System Test. This deliverable shall consist of but is not limited to: - The specific activities of the system test - Test Results - Test Issues - Test Resolutions - Test Scripts/Expected Results - SVRS Application ready for User Acceptance Testing. |

## Milestone VIII: SVRS Release 1 Acceptance Test

This Milestone is considered complete once the associated Deliverables have been Accepted by the SEB.

| Table 11 |  |  |
| --- | --- | --- |
| ID | Deliverable | Description |
| CT8 | Conduct the Train the Trainer Sessions | This activity consists of validating the execution and completion of the Train the Trainer Sessions. This document shall consist of but is not limited to: - Participation surveys - Class evaluations - Results and analysis of surveys and evaluations |
| PDP8 | Pilot Deployment Plan | The Pilot Deployment Plan details the when and how the application will get rolled out to the pilot deployment group and sites, as well as the tasks necessary to prepare for the pilot roll-out. This document shall consist of but is not limited to: - Scope - Target audiences - Timelines and milestones - Activities - Roles and responsibilities - Dependencies - Risks |
| PCR8 | Pilot Mock Data Conversion Results | The Pilot Mock Data Conversion Results shall provide detailed results and issues found during the initial conversion pilot. This document shall consist of but is not limited to: - An issues log of problems with the conversion - The total number of records updated - Number of records for each exception type - Summary of fields changed or transformed |
| UAT8 | User Acceptance Testing – Release 1 | This activity consists of the SEB executing their User Acceptance Test scripts for Release 1. |

## Milestone IX: SVRS Release 1 Pilot Implementation

This Milestone is considered complete once the associated Deliverables have been Accepted by the SEB.

| Table 12 |  |  |
| --- | --- | --- |
| ID | Deliverable | Description |
| PDR9 | Pilot Deployment Report | The Pilot Deployment Report summarizes the result of the pilot roll-out. The evaluation is used as an input to the Statewide Deployment Plan. |
| TOM9 | Technical Operations Manual | The Technical Operations Manual describes the technical system procedures and activities required to operate and maintain the SVRS. This document shall consist of but is not limited to: - System operations - Troubleshooting procedures |
| SDP9 | Statewide Deployment Plan - Release 1 | The Statewide Deployment Plan is an update of the Pilot Deployment Plan that details the when and how for the application to get rolled out to the target deployment groups and sites, as well as the tasks necessary to prepare for the roll-out. This document shall consist of but is not limited to: - Scope - Target audiences - Timelines and milestones - Activities - Roles and responsibilities - Dependencies - Risks |
| SCD9 | Software Customization Design | The Software Customization Design describes the detailed design for all SVRS Customization. This document shall consist of but is not limited to: - List of new functions - List of new features - Detailed Specifications |
| TDS9 | Train DET and SEB staff | The Training consists of activities and confirmations that the SEB and DET have completed training. This document shall consist of but is not limited to: - Participation surveys - Class evaluations - Results and analysis of surveys and evaluations |

## Milestone X: SVRS Data Conversion

This Milestone is considered complete once the associated Deliverables have been Accepted by the SEB.

| Table 13 |  |  |
| --- | --- | --- |
| ID | Deliverable | Description |
| SCR10 | Statewide Mock Data Conversion Results 1 & 2 | The Statewide Mock Data Conversion Results 1 shall provide detailed results and issues found during the first phase of the statewide mock conversion. This document shall consist of but is not limited to: - An issues log of problems with the conversion - The total number of records updated - Number of records for each exception type - Summary of fields changed or transformed |

## Milestone XI: SVRS Release 1 Implementation and SVRS Release 2 Delivery

This Milestone is considered complete once the associated Deliverables have been Accepted by the SEB.

| Table 14 |  |  |  |  |
| --- | --- | --- | --- | --- |
| ID | Deliverable |  | Description |  |
| GLR11 | Go Live Report -Release 1 |  | The Go Live Report summarizes the lessons learned from the roll-out experience, information pertaining to each municipality go live. The Go Live Report captures: - Lessons Learned - Key Dates for each Municipality/County - Open Deployment Items |  |
| STR11 | System Test Results – Release 2 |  | The System Test Results shall provide the results of the SVRS System Test. This document shall consist of but is not limited to: - The specific activities of the system test - Test Results - Test Issues - Test Resolutions - Test Scripts/Expected Results |  |
| STM11 |  | SVRS Train-the-Trainer Materials Release 2 |  | The SVRS Training Materials consist of all materials required to train users in the use of the SVRS. This document shall consist of but is not limited to: - AESM/SVRS End User Manual - AESM/SVRS Instructor Guide - Training procedures / scenarios - Sample Training Schedule - Training materials on training techniques - Updated Online Help – User Guides |

## Milestone XII: SVRS Final Acceptance & Project Closeout (Holdback Payment #3)

This Milestone is considered complete once the associated Deliverables have been Accepted by the SEB.

| Table 15 |  |  |  |  |
| --- | --- | --- | --- | --- |
| ID | Deliverable |  | Description |  |
| UAT12 |  | User Acceptance Testing – Release 2 |  | This activity consists of the SEB executing their User Acceptance Test scripts for Release 2. |
| GLR12 | Go Live Report -Release 2 |  | The Go Live Report summarizes the lessons learned from the roll-out experience, information pertaining to each municipality go live. The Go Live Report captures: - Lessons Learned - Key Dates for each Municipality/County - Open Deployment Items |  |
| UAS12 | End User Survey |  | The End User Acceptance Survey shall document the overall results of a survey that is provided to ensure that the SVRS has been implemented and live. This document shall consist of but is not limited to: - Survey - Survey Results - Issues and recommended solutions |  |
| PC12 | Project Closeout |  | The Project Closeout shall document the steps that need to be taken to finalize the project. This document shall consist of but is not limited to: - Finalized List of Issues and recommendation solution - Project Closeout memo |  |

## Deliverable Dates and Review Periods

The following table is a list of all Deliverables Delivery Dates and Review Periods.

| Table 16 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ID | Deliverable | Delivery Date | SEB Review Days* | Correction Period* | SEB Re-Review Period* | SEB Acceptance Date | Value of Deliverable |
| IP1 | Implementation Plan | 11/26/04 | 6 | 4 | 2 | 12/13/04 | $263,555 |
| CP1 | Communication Plan | 11/22/04 | 6 | 6 | 3 | 12/10/04 | $263,555 |
| PI1 | Project Initiation | 11/30/04 | 6 | 3 | 2 | 12/14/04 | $263,555 |
| AAC2 | Application Acceptance Criteria – Release 1 | 12/10/04 | 6 | 8 | 7 | 1/7/05 | $263,555 |
| IS2 | Interface Strategy | 12/10/04 | 4 | 5 | 12 | 1/7/05 | $263,555 |
| BR2 | Requirements Traceability Matrix – Release 1 | 12/10/04 | 6 | 13 | 3 | 1/10/05 | $263,555 |
| SAD3 | Solution Architecture Design | 1/21/05 | 6 | 6 | 4 | 2/11/05 | $263,555 |
| TA3 | Technical Training Assessment | 1/14/05 | 4 | 3 | 2 | 1/26/05 | $263,555 |
| HDP3 | Help Desk Plan | 1/21/05 | 6 | 6 | 2 | 2/9/05 | $263,555 |
| TP3 | Training Plan | 1/21/05 | 6 | 6 | 4 | 2/11/05 | $263,555 |
| DCS3 | Data Conversion Strategy and Approach | 1/7/05 | 7 | 6 | 4 | 1/31/05 | $263,555 |
| WCP3 | Workstation Installation Checklist | 1/14/05 | 4 | 4 | 3 | 1/28/05 | $263,555 |
| CDE3 | Configuration Design – Release 1 | 1/28/05 | 6 | 5 | 2 | 2/15/05 | $263,555 |
| ID3 | Interface Design | 1/21/05 | 4 | 4 | 3 | 2/4/05 | $263,555 |
| AAC4 | Application Acceptance Criteria – Release 2 | 2/18/05 | 4 | 4 | 3 | 3/4/05 | $263,555 |
| BR4 | Requirements Traceability Matrix – Release 2 | 2/25/05 | 6 | 4 | 2 | 3/14/05 | $263,555 |
| TD4 | SVRS Training Design | 2/18/05 | 4 | 4 | 3 | 3/4/05 | $263,555 |
| CDE5 | Configuration Design – Release 2 | 3/25/05 | 6 | 6 | 4 | 4/15/05 | $263,555 |
| STP6 | System Test Plan | 4/15/05 | 6 | 6 | 9 | 5/15/05 | $263,555 |
| STM6 | SVRS Train-the-Trainer Materials | 4/8/05 | 4 | 4 | 3 | 4/22/05 | $263,555 |
| IC6 | Installation Certification | 4/15/05 | 6 | 6 | 4 | 5/6/05 | $263,555 |
| STR7 | System Test Results – Release 1 | 5/31/05 | 5 | 5 | 2 | 6/15/05 | $263,555 |
| CT8 | Conduct the Train the Trainer Sessions | 6/10/05 | 4 | 3 | 4 | 6/25/05 | $263,555 |
| PDP8 | Pilot Deployment Plan | 6/3/05 | 4 | 4 | 13 | 7/1/05 | $263,555 |
| PCR8 | Pilot Mock Data Conversion Results | 6/15/05 | 4 | 5 | 3 | 6/30/05 | $263,555 |
| UAT8 | User Acceptance Testing – Release 1 | 6/1/05 | 30 | Continuous During the 30 Calendar Days |  | 7/1/05 |  |
| PDR9 | Pilot Deployment Report | 8/5/05 | 4 | 3 | 2 | 8/17/05 | $263,555 |
| TOM9 | Technical Operations Manual | 7/22/05 | 6 | 6 | 2 | 8/10/05 | $263,555 |
| SDP9 | Statewide Deployment Plan - Release 1 | 7/1/05 | 6 | 6 | 4 | 7/22/05 | $263,555 |
| SCD9 | Software Customization Design | 7/22/05 | 6 | 6 | 2 | 8/10/05 | $263,555 |
| TDS9 | Train DET and SEB staff | 7/22/05 | 6 | 6 | 2 | 8/10/05 | $263,555 |
| SCR10 | Statewide Mock Data Conversion Results 1 & 2 | 9/2/05 | 6 | 4 | 1 | 9/16/05 | $263,555 |
| GLR11 | Go Live Report -Release 1 | 10/19/05 | 3 | 4 | 1 | 10/28/05 | $263,555 |
| STR11 | System Test Results – Release 2 | 9/23/05 | 6 | 4 | 2 | 10/10/05 | $263,555 |
| STM11 | SVRS Train-the-Trainer Materials Release 2 | 9/23/05 | 6 | 4 | 2 | 10/10/05 | $263,555 |
| UAT12 | User Acceptance Testing – Release 2 | 11/1/05 | 30 | Continuous During the 30 Calendar Days |  | 11/30/05 |  |
| GLR12 | Go Live Report -Release 2 | 3/8/06 | 4 | 3 | 1 | 3/17/06 | $263,555 |
| UAS12 | End User Survey | 3/8/06 | 4 | 3 | 1 | 3/17/06 | $263,555 |
| PC12 | Project Closeout | 3/8/06 | 4 | 3 | 1 | 3/17/06 | $263,555 |

*  Business Days

# Documentation

The Contractor shall furnish the SEB with the following documentation, which shall be in the form and substance at least equal to comparable material generally in use in the industry in the following quantities:

| Documentation | Quantity |
| --- | --- |
| User’s Manual | 10 |
| Systems Manual | 10 |
| Operating Manual | 10 |
| User Training Manual | 10 |
| Programming Manual | 10 |
| Data Dictionary | 10 |
| On Line Training | Inherent in SVRS Application |

The original documentation and any update shall be delivered within two (2) business days of the delivery of the SVRS Application. Online documentation shall be updated within two (2) business days of the delivery of the SVRS Application.

# Hardware and Third Party Software

The Contractor provided the hardware and software minimum requirements for operation of the SVRS to the SEB in its Vendor’s Response of June 8, 2004.  The Contractor shall confirm these minimum requirements and provide as a Deliverable a certification process for all hardware and software to ensure that they meet Application Performance and SVRS Application Availability.

# SEB Responsibilities

- All existing voter registration and election management data stored in electronic form shall be provided to the Contractor conversion team 3 times (2 mock and 1 final) in a non-proprietary format.

- SEB subject matter experts (SMEs) with knowledge of Wisconsin election laws, process and procedures shall be available to assist the project team on a part-time basis as necessary.

- The SEB shall designate a single point-of-contact for each local jurisdiction to address conversion and training items.

- Introductory and Advanced SVRS training shall be mandatory for prospective users and the SEB shall be responsible for making sure all Authorized Users are trained.

- The SEB shall manage the communication effort to project stakeholders. The Contractor shall assist with reviewing and contributing to communication messages, methods, etc.

- The SEB shall ensure the Contractor’s team members shall be able to meet with selected Standards Committee members who, as part of the deployment phase kick-off, will be willing to take part in the assessments required (change readiness, and training/skills).

- The SEB shall appoint a Super User to support training of new hires and learn specialized functionality of SVRS.

- Subject matter experts and Information Technology resources from SEB, DET, and external agencies shall be made available according to the schedule in the project work plan, along with direct access to the necessary data and documentation, to assist in the SVRS interfaces design and testing as necessary.

- Office space and any associated resources (furniture, phone systems, computer and network access, wiring, fax, copier) shall be provided by SEB at no expense to Contractor. Office supplies are the responsibility of the Contractor.

- SEB shall procure and install network service and hardware by the schedule identified by Contractor during the project planning activities.

- All expenses for extraction of data from current voter registration and election management systems shall be paid for by the SEB, County, or Municipality.

- Municipality and County clerks or their perspective staff shall be available on a timely basis for resolving questions about data formats and for data cleansing. They shall make reasonable efforts, as directed by SEB, to provide access to all available documentation for existing voter registration and election management systems within the scope of this project in a timely fashion, should the need arise.

- The SEB expects only one Data Population Strategy for all municipalities (not one per municipality).

- The SEB is responsible for all user training, other than the training provided by Contractor to the SEB and DET personnel.

- The SEB shall distribute SVRS Project Communications materials through the SEB’s existing distribution channels.

- The SEB shall require that all trainees, including new State workers, shall have a basic knowledge of how to perform their job functions before training, including SEB, Municipality, and County policy and procedures. Trainees have a basic working knowledge of a Windows desktop environment, Internet browsers, and basic MS Office functionality prior to training.

- The SEB shall be responsible for ensuring that Municipality and County and other government agencies, employees, and government contractors involved in the Project will cooperate with the Contractor as reasonably required to allow Contractor to complete its services.

- The SEB shall provide a calendar of known Election Days to the Contractor on an annual basis.

- The SEB shall notify the Contractor thirty (30) days in advance of the occurrence of a Special Election Date.