Wisconsin State Elections Board

SVRS Contract #EB-SVRS1

11/12/04

TABLE OF CONTENTS

RECITALS	5

DEFINITIONS	6

- Contract Precedence	9

- Contract Term	9

- Contract Price	…9

- Contract Periods	…………9

- Implementation Services	10

- Warranty Period	12

- Maintenance Services	12

- Support Services	12

- Project Milestones	12

- Extra Work	13

- Retainage	13

- Leading Industry Practices	14

- Contractor as Prime Contractor	14

- Contractor’s Representations	14

- Change in Ownership / Financial Condition	16

- Key Personnel and Personnel Changes	16

- Independent Capacity of Contractor	17

- Employment	18

- Change in Circumstances	18

- Insurance Responsibility	18

- Acceptance Process	18

- Performance Documentation	20

- Amendments and Change Orders	20

- Warranty	20

- Warranty Disclaimer	21

- Intellectual Property Licenses and Permits	21

- Intellectual Property Indemnification	22

- Intellectual Property Ownership	22

- Rights in Data and Copyright – Federal Reserved Rights	24

- Source Code Escrow	24

- Termination for Cause / Default	25

- Termination for Convenience	27

- Cancellation for Misappropriation / Nonappropriation	28

- Responsibilities Upon Termination or Cancellation	28

- Transition Services	29

- Liquidated Damages	29

- Limitation of Liability	31

- Indemnification	32

- General Legal Relations	32

- Confidentiality of Records	32

- Payment Requirements and Invoicing	33

- Progress Reports	33

- Record keeping and Record Retention	34

- Audits	34

- SEB Furnished Property	34

- Security Clearance Background Checks	35

GENERAL PROVISIONS	35

- Access to Facilities	35

- Antitrust Assignment	35

- Applicable Law	36

- Assignment	36

- Conflict of Interest	36

- Consent To Breach Not Waiver	36

- Contract Interpretation	36

- Cooperation with Other Contractors or Subcontractors	36

- Disclosure	37

- Force Majeure	37

- Kickbacks	38

- Minority Business Subcontractors	38

- Nondiscrimination / Affirmative Action	38

- Material Safety Data Sheet	39

- No Finder’s Fee	39

- Promotional Advertising / News Releases	39

- Safety Requirements	39

- Severability	39

- Site Rules and Regulations	39

- Contractor Tax Delinquency	40

- Taxes	40

- Third Party Beneficiaries	40

- Dispute Resolution	40

Exhibit A – Payment Schedule

Exhibit B –  Statement of Work

Exhibit C – Business and Technical Requirements

Exhibit D – Service Level Agreement

Exhibit E – Accenture AESM Software License Agreement

CONTRACT FOR STATEWIDE VOTER REGISTRATION SYSTEM

AND RELATED SERVICES

Between

WISCONSIN STATE ELECTIONS BOARD

And

ACCENTURE LLP

THIS CONTRACT is made this 12th day of November, 2004 by and between the Wisconsin State Elections Board, acting on behalf of the State of Wisconsin, state agencies, and local jurisdictions (hereinafter “SEB”), whose address is 17 W. Main Street, Suite 310, Madison, Wisconsin, 53703, and Accenture LLP, whose address is 11951 Freedom Drive, Reston, Virginia 20190 (hereinafter “Contractor”); the SEB and the Contractor are sometimes referred to collectively as the “Parties.”

RECITALS

WHEREAS, on May 6, 2004, the SEB published a Request for Proposal (“RFP”) #EB-SVRS1, seeking a vendor to provide a Statewide Voter Registration System (SVRS) and Election Management System on a not-to-exceed fixed-price basis, including design and development of software, customizations necessary to meet Wisconsin’s business and technical requirements, implementation services, data population strategy and conversion, training, service desk, and maintenance and support; and

WHEREAS, Contractor responded to the above described RFP on June 8, 2004; and

WHEREAS, the SEB engaged in a protracted and detailed review of each RFP submitted, rated each proposal, and concluded with a selection of a system that would best benefit the State of Wisconsin.  Subsequent meetings were held between representatives of the SEB and the Contractor to clarify certain aspects of Contractor’s response to the RFP; and

WHEREAS, on October 15, 2004, SEB selected Contractor to be the Statewide Voter Registration System (SVRS) project vendor pursuant to RFP #EB-SVRS1; and

WHEREAS, the required approvals, clearances and coordination have been accomplished from and with the appropriate agencies.

NOW, THEREFORE, in consideration of these premises, and other good and valuable consideration, SEB and Contractor agree as follows:

# DEFINITIONS

The State and Contractor agree to the definitions and the meanings of the terms (words and phrases) used in this Contract as follows:

- Accenture Knowledge Capital means Materials existing prior to commencement of the Services, or developed by the Contractor outside this Contract that are proprietary to the Contractor or third parties, including all intellectual property rights therein and together with any improvements, modifications or enhancements to those Materials whether or not such improvements, enhancements and/or modifications are developed as part of the Services.

- AESM Software means the Accenture Election Systems Manager proprietary software owned by the Contractor and licensed to the State of Wisconsin pursuant to Exhibit E – Accenture AESM Software License Agreement, that will be used in the design, implementation, and operation of the SVRS Application, including any improvements, enhancements and/or modifications thereto, whether or not such enhancements and/or modifications are developed as part of the Services.  AESM Software is considered Accenture Knowledge Capital.

- Authorized Users means all employees, agents, and third-party contractors of the State of Wisconsin, SEB, Municipal and County Clerks and their respective staff, or others authorized by the SEB to use the SVRS.

- Change Order means a written document specifying a change to Exhibit B – Statement of Work.

- Confidential Voter means a voter who is a victim of domestic abuse and authorized to be listed confidentially on poll lists.

- Contract Price means the not-to-exceed amount the SEB pays to the Contractor for the Implementation Services and Warranty Services, and does not include Maintenance Services and Support Services costs.

- County Clerk means the clerk of a county.

- Customizations means Materials that are originally developed by the Contractor during the course of the Implementation Services and Warranty Services and supplied as, or as part of, a Deliverable, but exclusive of Accenture Knowledge Capital.

- Data Conversion means the electronic conversion of voter records from a county or municipal legacy system into the new SVRS, including the electronic conversion of data from SEB legacy systems.

- Data Population means the data entry of SVRS records from municipalities that currently do not have voter registration.

- DET means Division of Enterprise Technology within the Wisconsin Department of Administration.

- Deliverables mean Materials originated and prepared by Contractor for the SEB under this Contract, including Customizations and Accenture Knowledge Capital.

- Demobilization Costs means all non-refundable costs incurred by the Contractor and its subcontractors, including early termination charges, for airline tickets, car leases, apartment leases, personnel moving and relocation expenses, equipment leases and facility leases, less any amounts paid prior to the effective date of termination.

- Divert or Diversion means the transfer of Key Personnel by the Contractor or a subcontractor to another assignment within the control of the Contractor or a subcontractor, but does not include the resignation, death, disablement, termination, legally required leave, or dismissal for cause of an employee that is beyond the control of the Contractor or subcontractor.

- DHFS means the Wisconsin Department of Health and Family Services.

- DOA means the Wisconsin Department of Administration.

- DOC means the Wisconsin Department of Corrections.

- DOJ means the Wisconsin Department of Justice.

- DOT means the Wisconsin Department of Transportation.

- DMV means the Wisconsin Division of Motor Vehicles within the DOT.

- Election Period means the thirty (30) calendar days preceding and the fifteen (15) calendar days following a Wisconsin Spring Primary, Spring Election, Partisan Primary, General Election or Special Election.

- Election Day Registration means a voter registration that occurs at a poll location on an Election Day.

- Elector means an individual who is qualified to vote.  Elector and voter can be used interchangeably.

- Extra Work means any work performed by the Contractor that is outside the scope of Services of this Contract pursuant to an amendment to this Contract.

- Fiscal year means the SEB’s fiscal year; July 1 to June 30.

- Fixes means any correction made by the Contractor to the SVRS Application to restore it to its working condition or to bring it into compliance with the Design Specifications during Maintenance Services.

- HAVA means Federal Help America Vote Act of 2002.

- Key Personnel means the Contractor’s and subcontractor’s personnel assigned to the Wisconsin project that have specific, high level responsibilities under the terms of this Contract.

- Late Registration means a voter registration that occurs between thirteen (13) days prior to the election and the day before the election.

- Materials mean all work product and materials, including reports, documents, templates, and software programs in both source and object code, specifications, business methods, tools, methodologies, processes, techniques, solution construction aids, analytical frameworks, algorithms, know-how, processes, products, documentation, abstracts and summaries thereof used in the development of the SVRS.

- Milestone Delivery Date means that date by which all Deliverables associated with a Milestone shall have been submitted by the Contractor and received by the SEB for Acceptance Testing.

- Modifications mean enhancements or changes to the AESM Software that are requested by the SEB during the performance of the Maintenance Services.

- Municipal Clerk means the clerk of a Municipality.

- Municipality means a town, village or city.

- Non-Election Period means all days and hours not included in an Election Period.

- Pre-registration means a voter registration that occurs not later than thirteen (13) days prior to an election, including registration by mail.

- Release 1 means the functionality within the AESM Software as specified in Exhibit C – Business and Technical Requirements and Customizations, in accordance with Release 1 Final Acceptance, as set forth in Section 21 (Acceptance Process).

- Release 2 means the functionality within the AESM Software as specified in Exhibit C – Business and Technical Requirements and Customizations, in accordance with Release 2 Final Acceptance, as set forth in Section 21 (Acceptance Process).

- Requirement means a necessary or mandatory item, including those items set forth in Exhibit C – Business and Technical Requirements. All Requirements will be identified in and addressed in full by the Specifications.

- SEB means the Wisconsin State Elections Board.

- Services mean the Implementation Services, Warranty Services, Maintenance Services, and Support Services to be performed by the Contractor under this Contract.

- Source Code means the AESM Software, Customizations, and Modifications (as applicable during performance of Maintenance Services) developed by Contractor, including applicable commentary and explanations relating to use, maintenance and operation of AESM Software, Customizations, and Modifications.

- Specification means a mutually agreed written detailed description of particulars for each Deliverable, identifying which Requirement(s) are met by the Deliverable and prescribing materials, dimensions, design, quality of work and other requirements as applicable.

- SVRS means Statewide Voter Registration System, which consists of: (a) software, hardware, data, and materials owned or licensed by the State of Wisconsin, and (b) Contractor Deliverables.

- SVRS Application means the AESM Software and Customizations.

- SWEBIS means the current State of Wisconsin Elections Board Information Systems.  SWEBIS 1 manages campaign finance functions.  SWEBIS 2 manages election administration.

- Voter means an individual registered to vote that participates in an election conducted by the State of Wisconsin.  “Elector” and “voter” can be used interchangeably with the same meaning.

## 1.  Contract Precedence

The following is the Contract Order of Precedence in the event that a conflict or dispute arises between documents comprising the Contract:

- Official SEB Purchase Order;

- SVRS Contract, dated November 12, 2004;

- SEB Request for Proposal (RFP) # EB-SVRS1 dated May 6, 2004, (including all appendices and amendments);

- Contractor’s Demonstration presentation materials, dated July 21, 22 and 23, 2004;

- Contractor’s Proposal, dated June 8, 2004.

## 2.  Contract Term

The Contract shall commence on the date of Contract execution, and shall continue through the date of the Final Acceptance of Release 2, but in no case shall it continue later than June 30, 2010, unless the Contract is a) extended by mutual written consent for up to two (2) additional one-year periods, or b) terminated under the provisions hereunder.

## 3.  Contract Price

The cost of the AESM Software License, Implementation Services and Warranty Services to be performed and Deliverables to be provided by Accenture, as set forth herein shall be the fixed fee price of $9,751,510.  The SEB shall pay the Contractor as set forth in Exhibit A – Payment Schedule.  The cost of Maintenance Services or Support Services ordered by the SEB shall be set on an annual basis at a mutually agreed “not to exceed” price as set forth in Exhibit A – Payment Schedule.

The Contractor shall provide the Services and Deliverables in accordance with the terms and conditions of this Contract, within the prices specified in Exhibit A – Payment Schedule or as adjusted based on Contract amendment.

## 4.  Contract Periods

The Parties shall adhere to the following Implementation Schedule:

- Implementation Periods:

- The Release 1 Final Acceptance shall be completed no later than

December 1, 2005.

- The Release 2 Final Acceptance shall be completed no later than

March 30, 2006.

- Warranty Period:  The Warranty Period shall begin on the date of Release 2 Final Acceptance and run through December 31, 2006 (“Warranty Period”).

- Maintenance Period:  The Maintenance Period shall begin on the completion of the Warranty Period and run for a period of one (1) year (prorated as necessary), with 3 optional one-year extensions.

- Support Period:  The Support Period shall begin on August 1, 2005 and run for a period of eleven (11) months, with 4 optional one-year extensions.

## 5.  Implementation Services

The Contractor shall provide the following Services during the Implementation Period of the Contract.  A more definitive description of the Implementation Services and specific responsibilities of the parties are described in the Exhibit B – Statement of Work.  The Contractor shall use industry leading practices, as set forth in Section 12 (Industry Leading Practices), to provide Services and identify additional areas that are required for a successful SVRS implementation.

- Project Management:  The Contractor shall manage the tasks and deadlines pertinent to its implementation and software application development responsibilities.  The Contractor shall define, and provide training and access for, the use of the implementation approach, project methodology, and tools and templates.  The SEB shall perform project and contract management of the SVRS implementation, provide project personnel and Deliverable review and approval.

- Design / Specifications:  The Contractor shall develop the written Specifications for all Deliverables that will be developed by Contractor under this Contract.  The SEB shall review and approve all Deliverables and Specifications.

- Installation and Configuration:  The Contractor shall assist SEB in coordinating the installation of the SVRS Application in the Wisconsin Department of Administration’s Division of Enterprise Technology (hereinafter “DET”) data center.  DET shall purchase and install all hardware and third-party system software.  The Contractor shall provide Customizations to the AESM Software to conform to the Specifications.  The Contractor shall, in concert with DET as Deliverables, establish the interfaces between the AESM Software and other state agency databases (e.g. Division of Motor Vehicles).

- AESM Software Customizations:  The Contractor shall make all Customizations in accordance with the Specifications.  The Contractor shall test the AESM Software and Customizations in accordance with the Acceptance Testing procedures, prior to submission to the SEB for Acceptance.  The SEB, and in conjunction with Contractor as required, shall perform Acceptance Testing of the SVRS Application.

- Data Conversion and Population Strategy:  The Contractor shall develop and implement a Data Conversion strategy for those Municipalities and Counties that have voter registration data that need electronic conversion of the voter data (i.e., current name and address, voter participation history, geographic boundaries, poll locations and office holders) from the existing systems to the SVRS Application.  The Contractor shall develop and implement a strategy to convert all voter participation history, name and address history, absentee voter history, poll worker information and transaction history for those Municipalities and Counties that have the information in an electronic format.  The Contractor shall provide the services offered in its response to RFP Section A3.3, excluding options in A6.2.

The Contractor shall develop and implement a Data Conversion plan for the data in the legacy election administration systems currently in use by the SEB.

The Contractor shall develop one Data Population strategy for the collection and data entry of voter registration information from those Municipalities that do not currently have electronic versions of voter registration.  The SEB intends to implement the strategy to collect the data and shall be responsible for the data entry of the information in the SVRS Application.

The Contractor shall not be responsible for the data entry of voter registration information or election management information.  The Contractor shall provide two methods for data entry, a data entry program and a secure web page.

- Initial Training:  The Contractor shall provide technical training to DET and SEB Technical staff with the skills needed to maintain and support the SVRS after implementation.  The Contractor shall provide training and materials to the SEB regarding the operation, administration, and use of the SVRS Application.  The Contractor shall provide educational training to the SEB and the SEB’s trainers in training techniques, in the use of the training materials and user training necessary for the SEB to train the Authorized Users in the operation and use of the SVRS Application.  The Contractor shall provide a practice training environment and telephone support to the SEB’s trainers during the SEB Authorized user training sessions for Release 1 and Release 2.

Initial training shall begin during the Implementation Period and continue through the completion of the implementation of Release 2.  Training materials shall be updated if required when new releases of the SVRS Application are provided to the SEB.  The Contractor shall provide hands-on training in the SVRS to the SEB.  The SEB’s trainers shall train the Authorized Users in the SVRS Application.  All training materials shall be furnished in English only.

- Installation Certification:  The Contractor shall provide the recommended minimum third party hardware and software requirements and specifications (including configuration parameters) for the DET’s data center host environment for the SVRS Application.  The SEB shall purchase all necessary hardware and software and shall configure the environment according to the configuration specifications from the Solution Architecture Design Deliverables described in Exhibit B – Statement of Work or shall confer with the Contractor for alternate solutions.

Once the environment is installed and configured by DET, the Contractor shall inspect the configuration and certify that all DET-installed data center hardware and third-party software meets the SVRS Specifications.  Should the installation and configuration not meet the SVRS Specifications, DET shall make the modifications necessary and the Contractor shall re-inspect.

The Contractor shall provide minimum workstation requirements necessary for all Authorized User workstations to meet system Specifications.  The SEB shall certify that all such workstations meet the appropriate Specifications.  The workstation requirements and installation checklist shall be provided in the Workstation Installation Checklist Deliverable described in Exhibit B – Statement of Work.

- Security:  As a Deliverable, the Contractor shall provide a recommended SVRS configuration design that contains mutually agreed to levels of security in an attempt to prevent malicious or unauthorized access to the DET data center and network, however the Contractor makes no guarantees or warranties regarding the possibility that malicious or unauthorized access could occur and the Contractor shall not be responsible in the event of such occurrence.  The Contractor shall not be responsible for security installation or implementation, physical security, or hardware security.

## 6.  Warranty Services

To the extent there are warranty claims relating to Contractor developed Deliverables during the Warranty Period, as set forth in Section 4 (Contract Periods) of this Contract, the Contractor shall provide warranty services in accordance with Section 24 (Warranty) and Section 25 (Warranty Disclaimer) of this Contract (“Warranty Services”).

## 7.  Maintenance Services

Maintenance Services shall not be required by the SEB until after the Warranty Period has expired.  During the Maintenance Period of the Contract, the Contractor shall perform the Maintenance Services set forth in Exhibit D – Service Level Agreement.

## 8.  Support Services

During the Support Period of the Contract, the Contractor shall perform the Support Services set forth in Exhibit D – Service Level Agreement.

## 9.  Project Milestones

The “Milestones” represent key project checkpoints defined by the completion of Implementation Services and a series of Deliverables.  A Milestone shall be complete when all Deliverables associated with it have been accepted by the SEB.  Associated Deliverables to each Milestone are as set in Exhibit B – Statement of Work.  A “Milestone Delivery Date” is the estimated date of delivery for each Milestone, as set forth below. A Milestone Delivery Date shall be met when all Deliverables associated with that Milestone have been submitted by the Contractor and received by the SEB and ready for Acceptance Testing.  The Milestone Delivery Dates are as follows:

|  | Project Milestone | Estimated Milestone Delivery Date |
| --- | --- | --- |
| I | Implementation Planning Deliverables | 12/15/04 |
| II | SVRS Release 1 Specifications | 1/14/05 |
| III | SVRS Release 1 CRP & Configuration Design | 2/15/05 |
| IV | SVRS Release 2 Specifications | 3/15/05 |
| V | SVRS Release 2 CRP & Configuration Design | 4/15/05 |
| VI | SVRS Release 1 Integration & System Test | 5/16/05 |
| VII | SVRS Release 1 Delivery for User Testing | 6/17/05 |
| VIII | SVRS Release 1 Acceptance Test | 7/15/05 |
| IX | SVRS Release 1 Pilot Implementation | 8/15/05 |
| X | SVRS Data Conversion | 9/16/05 |
| XI | SVRS Release 1 Implementation Final Acceptance & SVRS Release 2 Delivery | 10/28/05 |
| XII | SVRS Release 2 Final Acceptance & Project Closeout | 3/17/06 |

Contractor’s failure to meet the Milestone Delivery Date for Milestone VII (delivery of the SVRS Release 1 for User Testing) shall entitle the SEB the option to assess daily Liquidated Damages as set forth in Section 36 (Liquidated Damages).

## 10.  Extra Work

If by mutual agreement the Parties desire the Contractor to perform work or render services outside of the scope of Services of this Contract, said work or service shall be considered “Extra Work”, subject to written amendment of this Contract, setting forth the nature, pricing, schedule and scope thereof.  Payment rates for Extra Work shall be set forth in Exhibit A – Payment Schedule.

The terms and conditions of this Contract shall apply to all Extra Work, but shall require a separate statement of work and purchase order signed by authorized representatives of both Parties.

## 11.  Retainage

The SEB shall withhold as retainage (“Retainage”) a total of 20% of the Contract Price ($1,950,302.00), and shall make payments from the Retainage, according to the following table.  Payments are contingent upon the SEB’s Release 1 Final Acceptance (for the January 2006 and February 2006 Retainage release payments) and Release 2 Final Acceptance (for all other Retainage release payments).

| January 2006 | approximately 12.5% of the retainage or | $243,787.75 |
| --- | --- | --- |
| February 2006 | approximately 12.5% of the retainage or | $243,787.75 |
| April 2006 | approximately 25% of the retainage or | $487,575.50 |
| May 2006 | approximately 12.5% of the retainage or | $243,787.75 |
| June 2006 | approximately 12.5% of the retainage or | $243,787.75 |
| January 2007 or at the End of Warranty Period | approximately 25% of the retainage or | $487,575.50 |
| TOTAL | 20% of Contract Price | $1,950,302.00 |

## 12.  Leading Industry Practices

The Contractor and the SEB shall conduct Project activities in a manner that follows industry-recognized practices, as specifically set forth in the attachments.  Examples of such practices include:

- Active Contractor and SEB Executive Leadership participation so that business needs are addressed, stakeholders are aware of executive commitment to the Project, and oversight and direction is provided when needed.

- Active Contractor and SEB Project Management involvement so that plans and processes are in place to accomplish day-to-day project activities in a uniform, quality and efficient manner.

- A process exists and is followed to identify, assess, manage and mitigate Project risks.

- Project plans exist and are followed to achieve Project objectives in the areas of budgetary control, schedule control, change control, issue resolution, change management, and quality assurance.

- Application development integrates with third-party vendor (vendors of compilers, databases, etc.) guidelines and recommendations relating to SVRS, as appropriate.

- Contractor follows industry acceptable standards to address security during all phases of the project as set forth in the Contract.

- Project staff possesses project-required experience and follow professional standards of conduct.

- Contractor employs Capability Maturity Model Integration techniques to help accomplish Project objectives.

## 13.  Contractor as Prime Contractor

The Contractor shall be considered a prime contractor (i.e., the sole point of contact) with regard to all contractual matters, including the performance of Services, the payment of any and all charges resulting from contractual obligations, and responsibility for the performance of any subcontractors hired by Contractor for this Project.

All Contractor subcontractors shall abide by the terms and conditions of the Contract as applicable.  If additional subcontractors are required during the Contract other than proposed by Contractor in its proposal which are approved by SEB upon execution of this Contract, the Contractor shall obtain written approval from the SEB prior to the subcontractor’s commencement of work.

## 14.  Contractor’s Representations

As of the Contract Effective Date, the Contractor represents the true statements of fact that follow.  The Contractor further represents that the statements of fact shall remain true during the term of this Contract or promptly notify the SEB to the extent they may no longer be true.

- Organization, Qualification, Compliance with Laws.  The Contractor is an Illinois general partnership registered as a limited liability partnership duly organized under the laws of Illinois.  Contractor is qualified to do business in the State of Wisconsin as a foreign limited liability partnership.  Contractor is in good standing in the State of Illinois and all other states in which it transacts business, including the State of Wisconsin.  Contractor has the requisite power and authority to carry on its limited liability partnership business, as presently conducted, and Contractor complies with all laws and regulations governing its activities.

- No Adverse Changes.  The Contractor has not suffered any adverse change in personnel and capabilities since the date of Contractor’s RFP Response.  By executing this Contract, the Contractor represents that it is capable of performing all of the Services and providing all of the Deliverables required by the SEB in the Contract.  At time of execution of this Contract, the Contractor shall advise the SEB on the loss of any partners, suppliers, or subcontractors since the date of Contractor’s RFP Response.

- No Litigation.  The Contractor is not involved in any litigation or claim with respect to Services, including voter registration and election management system services, provided to other clients of the Contractor, which would affect the Contractor’s ability to perform under this Contract.  The term “litigation” includes an assignment for the benefit of creditors, and filings in bankruptcy or foreclosure.

- No Pending Litigation.  To its knowledge, the Contractor is not aware of any threatened litigation or claim, which would affect the Contractor’s ability to perform under this Contract.  In the event that the Contractor learns of any actual litigation (i.e., the Contractor named a party defendant) related to its government or elections practice which would affect the Contractor’s ability to perform under this Contract, the Contractor shall notify the SEB, in writing, as soon as reasonably possible after being served with a summons, complaint, or other pleading filed in federal or state court or with an administrative agency.  If requested in writing by the SEB and not subject to confidentiality restrictions, the Contractor shall deliver copies of litigation documents to the representatives designated in this Contract.

- Performance.  The Contractor shall be responsible for the professional quality, technical accuracy, timely completion, and coordination of all Services provided by Contractor as required by this Contract.  The Contractor shall provide all Services in accordance with applicable federal, state and local laws and regulations, and in a manner consistent with generally accepted professional and technical standards of the computer and election industries, except as otherwise stated in this Contract.

- Consents and Permits.  All necessary consents for the performance of the Contractor’s duties under this Contract have been obtained, including, if necessary, those required under Chapter 180 of the Wisconsin Statutes, relating to foreign corporations.  Throughout the term of this Contract, the Contractor shall obtain and shall maintain all licenses, permits, authorizations, and approvals necessary for performing work under this Contract.

- Location of Work Performed.  The Contractor shall not perform any of the Services described in this Contract outside of the territorial borders of the United States.

## 15.  Change in Ownership / Financial Condition

If the Contractor experiences a change in ownership or enters bankruptcy proceedings during the period prior to the award of a contract pursuant to the RFP, or if the Contractor experiences a change in ownership or enters bankruptcy proceedings during the term of the Contract or any extension thereof, the SEB must be notified of the event in writing at the time the event occurs or is identified.

Willful failure to notify the SEB upon receipt of an SEC Form 13g shall constitute cause for cancellation of the Contract.  Failure to notify the SEB of bankruptcy proceedings shall constitute cause for cancellation of the Contract.  For the purpose of this Section, “change of ownership” does not include a sale or transfer of Contractor's publicly held securities unless an individual partnership, corporation, associate group of investors or legal entity obtains an ownership interest of the Contractor in the amount of five percent (5%) or more.

## 16.  Key Personnel and Personnel Changes

The Contractor’s key personnel assigned to perform work under the Contract are identified by name in this Section 16 (Key Personnel and Personnel Changes) below.  The Contractor shall furnish the SEB with security credentials on both Key Personnel and non-Key Personnel, as set forth in Section 46 (Security Clearance Background Checks).

The Contractor shall not divert Key Personnel for any period of time except in accordance with the procedure identified in this Section.  The Contractor shall provide written notice of proposed diversion or replacement of Key Personnel to the SEB’s Contract Administrator at least forty-five (45) calendar days in advance, together with the name and qualifications of the person(s) who will take the place of the diverted or replaced Key Personnel.  At least thirty (30) calendar days before the proposed diversion or replacement, the SEB’s Contract Administrator shall notify the Contractor in writing whether the proposed diversion or replacement is approved or rejected, and if rejected shall provide reasons for the rejection.  Such approval by the SEB shall not be unreasonably withheld or delayed. Notwithstanding the foregoing, removal of Key Personnel due to employee leave, termination, resignation, illness, disability or legally required absence (“Key Personnel Removal Exceptions”) shall not be considered a breach of this Contract and is not subject to either SEB prior approval or liquidated damaged, however in such case Contractor shall promptly replace the Key Personnel within ten (10) business days after departure of said Key Personnel.

Replacement Key Personnel shall be on-site at least ten (10) business days prior to the departure date of the person being replaced.  Except as Key Personnel Removal Exceptions apply, failure of the Contractor to have replacement Key Personnel on-site at least ten (10) business days prior to the departure date of the replaced person shall entitle SEB with the option to assess Liquidated Damages as set forth in Section 36 (Liquidated Damages).

During the term of the Contract, Contractor shall designate an individual who shall be dedicated to the SVRS project (“Contractor Contract Administrator”).  The Contractor’s Contract Administrator shall be the primary contact for the SEB in dealing with the Contractor under this Contract, and shall have overall responsibility for managing and coordinating the delivery of Contractor Services and Deliverables.  The Contractor’s Contract Administrator shall meet regularly with the SEB’s Contract Administrator and shall have the authority to make decisions with respect to actions to be taken by Contractor in the ordinary course of day-to-day management of Contractor’s account in accordance with this Contract, however the Contractor Contract Administrator shall not have the authority to sign amendments to this Contract.

Replacement of Key Personnel shall be with persons of equivalent ability, experience, and qualifications.  The SEB shall have the right to conduct separate interviews of proposed replacements for Key personnel.  Such approval by the SEB shall not be unreasonably withheld, conditioned or delayed.  The SEB shall have the right to approve, in writing, the replacement of Key Personnel.  Any of the Contractor’s staff that the SEB deems unacceptable shall be promptly and without delay removed by the Contractor from the SVRS project and replaced by the Contractor within thirty (30) calendar days with another employee with equivalent experience and skills subject to the prior approval of the SEB.  Such approval by the SEB will not be unreasonably withheld or delayed.

The SEB shall identify a Contract Administrator who will be dedicated on a full time basis, to the SVRS Implementation of Release 1 and Release 2 (“SEB Contract Administrator”), shall approve payments to the Contractor for fixed cost Milestones, shall be responsible for timely review and approvals of the Services and Deliverables, and who shall be the Contractor’s only contact with SEB in all matters stated above except as directed by the SEB Contract Administrator.  The Contractor shall be entitled to rely on all decisions and approvals of the SEB Contract Administrator in connection with the Services or Deliverables.  In no instance shall the Contractor refer any matter to any other official other than the SEB Contract Administrator, unless authorized by the SEB Contract Administrator or required by law.  The Contractor’s Key Personnel shall be the following:

| Contractor Key Personnel During Implementation of Release 1 and Release 2 |  |
| --- | --- |
| John M. Fyfe | Project Director (part time) |
| Bryan Klimczak | Project Manager (full time) Contractor Contract Administrator |
| Dennis Ramos | Technical Team Lead (full time) |
| Alicia Kinsey | Functional Team Lead (full time) |
| Josh Murray | Transition Team Lead (full time) |

The SEB’s Contract Administrator shall be Barbara Hansen.

## 17.  Independent Capacity of Contractor

The Contractor, its officers, agents and employees shall act in the capacity of an Independent Contractor and not as an officer, employee or agent of the State of Wisconsin.  Contractor shall take such steps as may be necessary to ensure that each subcontractor is an independent contractor and shall not be considered or permitted to be an agent, servant, joint venture, or partner of the State of Wisconsin.

## 18.  Employment

The Contractor shall not engage the services of any person or persons now employed by the State of Wisconsin, including any department, commission or board thereof, to provide Services relating to the Contract without the written consent of the employer of such person or persons and of the State of Wisconsin.

## 19.  Change in Circumstances

Contractor shall give prompt after due internal management consultation notice to the SEB of either of the conditions that follow:

- Occurrence or non-occurrence of any event which would render any representation, covenant, or warranty untrue or inaccurate prior to the end of the term of this Contract; or

- Any failure of Contractor to comply with or satisfy any covenant, condition, or agreement set forth in this Contract.  Each request for payment by Contractor shall contain a certification that each of the representations and warranties contained in this Contract are, to the best of Contractor’s knowledge, true and accurate as of the date of the application for payment.

## 20.  Insurance Responsibility

The Contractor shall maintain the following:

- Worker's compensation insurance as required by Wisconsin Statutes, for all employees engaged in the work.

- Commercial general liability insurance.  Minimum coverage shall be one million dollars ($1,000,000) liability for bodily injury and property damage including product liability and completed operations.

- Motor vehicle insurance for all owned, non-owned and hired vehicles that are used in carrying out the Contract.  Minimum coverage shall be one million dollars ($1,000,000) per occurrence combined single limit for automobile liability and property damage.

The SEB reserves the right to require higher limits when warranted during the Contract Period.

## 21.  Acceptance Process

- Deliverable Acceptance.   When the Contractor has completed a Deliverable, the Contractor shall forward said Deliverable to the SEB on a mutually agreed upon "Acceptance Form".  Acceptance of a Deliverable shall be based on whether the Deliverable meets the Specifications, which shall be the sole and exclusive standard of acceptance of the Deliverable.  After the SEB receives a Deliverable, it shall review and test the Deliverable, in accordance with the applicable Specification, within the SEB Review Days set forth in Exhibit B – Statement of Work, for that Deliverable or other period as mutually agreed in writing.  After the SEB has reviewed the Deliverable in accordance with the applicable Specification, the SEB shall return the Acceptance Form executed by the SEB's Contract Administrator to the Contractor's Contract Administrator or shall forward to the Contractor's Contract Administrator a “Request for Modification Report” containing a detailed description of the manner in which the Deliverable fails to meet the Specification.

If during the Deliverable Acceptance Period the Contractor receives a Request for Modification Report, the Contractor shall exercise reasonable commercial efforts to modify the Deliverable to bring it into compliance with the Specifications and shall resubmit such modified Deliverable to the SEB with a new Acceptance Form within the Contractor’s Correction Period set forth in Exhibit B – Statement of Work.  The SEB shall review the Deliverable to determine whether it meets the Specifications.  The SEB Re-Review Period for each Deliverable shall be as specified in Exhibit B – Statement of Work, for that Deliverable or other period as mutually agreed in writing.  The process described above shall be repeated as often as mutually agreed upon by the Parties until the SEB has accepted all components of such Deliverable and has executed the related Acceptance Form.  The SEB's failure to return an executed Acceptance Form or to forward a Request for Modification Report within the SEB Review Days or SEB Re-Review Period shall be deemed an "Acceptance" of such Deliverable by SEB.

- User Acceptance Test.  The SEB shall accept the SVRS Application when the AESM Software meet the Requirements as specified in Exhibit C – Business and Technical Requirements and Customizations meet the Specifications (“User Acceptance Test Criteria”).  A User Acceptance Test shall be performed by SEB, based upon test scripts provided by Contractor and additional test scripts provided by SEB as mutually agreed, prior to Release 1 Final Acceptance and prior to Release 2 Final Acceptance to determine whether the AESM Software and Customizations meet the User Acceptance Test Criteria (“User Acceptance Test”). If during the User Acceptance Test Period, as specified in Exhibit B – Statement of Work, the SEB notifies Contractor in writing of any User Acceptance Test Criteria nonconformity, specifying as to each nonconformity how the SVRS Application, fails to meet the User Acceptance Test Criteria, Contractor shall use reasonable efforts to correct such nonconformity, or proceed on another mutually acceptable basis. The process described above shall be repeated as often as mutually agreed to by the parties (“SEB Re-Review Period”) until the SEB has accepted all components of the AESM Software and Customizations and has executed the related Acceptance Form.  Unless Contractor receives an Acceptance Form or notice of User Acceptance Test Criteria nonconformity, as provided above, the SVRS Application shall be deemed accepted upon expiration of the SEB Review Days and, if applicable, any SEB Re-Review Period.

The SVRS Application start date for User Acceptance Testing shall occur upon delivery of written notification to the SEB’s Contract Administrator by the Contractor’s Contract Administrator that the AESM Software and Customizations have been system tested by Contractor.  During Contractor’s system test, as specified in Exhibit B – Statement of Work, the Contractor shall communicate the status of the testing to the SEB at the regularly scheduled status meetings.

- Evaluation.  The SVRS Application shall be evaluated against the following:

- The AESM Software operates in conformance with the Requirements as specified in Exhibit C – Business and Technical Requirements and the Customizations operate in conformance with the Specifications,

- The SVRS Application run on a repetitive basis on a variety of actual live, representative data, as supplied by the SEB, in accordance with the Requirements as specified in Exhibit C – Business and Technical Requirements and Specifications, and

- The SVRS Application does not require modifications to other operational software systems and does not cause performance degradation of other software systems operating on the Division of Enterprise Technology’s (DET’s) computing systems and network, provided that the SVRS Application is installed and operated in strict conformance with the platform recommended by Contractor.

- Final Acceptance for Release 1 and Release 2.  Acceptance by the SEB, pursuant to Section 21(A) (Deliverable Acceptance) above, of all Deliverables required to be provided by Contractor during Milestones I through XI, as specified in Exhibit B – Statement of Work, and successful completion the Release 1 User Acceptance Test, pursuant to Section 21(B) (User Acceptance Test) above, shall be considered final acceptance of Release 1 (“Release 1 Final Acceptance”).

Acceptance by the SEB, pursuant to Section 21(A) (Deliverable Acceptance) above, of all Deliverables required to be provided by Contractor during Milestones XII, as specified in Exhibit B – Statement of Work, and successful completion the Release 2 User Acceptance Test, pursuant to Section 21(B) (User Acceptance Test) above, shall be considered final acceptance of Release 2 (“Release 2 Final Acceptance”).

## 22.  Performance Documentation

Contractor shall furnish the SEB with the manuals and other documentation, and in such quantity, as set forth in Exhibit B – Statement of Work.

## 23.  Amendments and Change Orders

The SEB shall not be obligated to pay the Contractor in excess of the limits set forth in

Exhibit A – Payment Schedule of the Contract, and the Contractor shall not be obligated to perform Extra Work for any work identified by the SEB that does not fall within the scope of Services of the Contract.  All changes to the Contract must be made as an Amendment in writing by authorized representatives of both parties.  Any proposed changes to the Contract Price or the Contract shall require written approval by Contractor’s Executive Officer (Meg T. McLaughlin or designee) and SEB’s Executive Director (Kevin J. Kennedy or designee).

Changes may be made to Exhibit B – Statement of Work that do not modify the Contract shall be memorialized in writing by mutual agreement between the Parties’ Contract Administrators.

## 24.  Warranty

- Services Warranty.  The Contractor warrants that its Implementation Services will be performed in a good and workmanlike manner to standards generally accepted in the industry.  The Contractor agrees to re-perform, at no additional cost, any Implementation Services not in compliance with this warranty brought to its attention in writing during the Implementation Period; Contractor shall use commercially reasonable efforts to bring into conformance any Implementation Services not in compliance with this warranty as soon as reasonably possible after receipt of written notice or such longer period mutually agreed to between SEB and Contractor. Contractor shall initiate re-performance within as soon as reasonably possible after Contractor’s receipt of written notice or such longer period mutually agreed to between SEB and Contractor.

- SVRS Application Warranty. Contractor further warrants that the AESM Software provided by Contractor during the performance of the Implementation Services shall meet the relevant Requirements as specified in Exhibit C – Business and Technical Requirements and the Customizations shall meet their relevant Specifications, during the Warranty Period set forth in Section 4 (Contract Periods) of this Contract.  Contractor agrees to correct, at no additional cost, the SVRS Application to the extent not in compliance with this warranty brought to its attention in writing during the Warranty Period; Contractor shall use commercially reasonable efforts to complete such corrections as soon as reasonably possible after receipt of written notice or such longer period mutually agreed to between SEB and Contractor.  Contractor shall initiate warranty corrections consistent with the claim type and response times as set forth in Exhibit D – Service Level Agreement.

- Contractor shall not be liable.  The Contract shall not be liable or responsible for the failure of the Services or the SVRS Application to conform with the foregoing warranties in Section 24 subsections A (Services Warranty) and B (SVRS Application Warranty) that is caused by the following:

- misuse or modification of the SVRS Application;

- failure to use corrections or enhancements made available by Contractor;

- use of the SVRS Application in combination with any product or information not owned or developed by Contractor;

- information, direction, specification or materials provided by SEB or any third-party;

- SEB operator or data error; or

- SEB nonperformance.

## 25.  Warranty Disclaimer

Section 24 (Warranty) is the Contractor’s only express warranty concerning the services, AESM SOFTWARE, CUTOMIZATIONS, any deliverables and any work product, and is made expressly in lieu of all other warranties, conditions and representations, express or implied, including any implied warranties of fitness for a particular purpose, merchantability, informational content, systems integration, non-infringement, interference with enjoyment or otherwise.

## 26.  Intellectual Property Licenses and Permits

Neither party shall knowingly violate the intellectual property rights of any third-party in the performance of their obligations under this Contract.  Any such violation by SEB is subject to Section 31 (Termination for Cause / Default) herein. Any such violation by Contractor is subject to Section 27, (Intellectual Property Indemnification) herein.

## 27.  Intellectual Property Indemnification

Contractor shall defend, at its sole expense, any third party claim(s) or suit(s) brought against the SEB alleging that the use by the SEB of any Deliverable (excluding third party products), or any part thereof, developed and supplied by Contractor under this Contract constitutes infringement of any presently existing U.S. patent, copyright, trade secret, or trademark (collectively “Intellectual Property”).  If the SEB promptly notifies Contractor in writing of a third-party claim against the SEB that any such Deliverable infringes a presently existing United States patent, copyright, trademark or trade secret of any third-party, the Contractor shall defend such claim at its expense and shall pay any costs or damages that may be finally awarded against the SEB.  The SEB shall give the Contractor written notice within twenty (20) business days of receipt by the SEB of such notice of such claim or suit.  The SEB shall provide reasonable assistance and cooperation to the Contractor in connection with such action.   The Contractor has sole authority to defend or settle such claim.  Contractor shall consult the SEB regarding such defense and the SEB may, at its discretion and expense, participate in any defense.  Should the SEB not choose to participate, Contractor shall keep the SEB advised of any settlement or defense. The Contractor shall have no obligation to indemnify SEB (including the State of Wisconsin) under any settlement made without the Contractor’s written consent.

Contractor shall not indemnify the SEB if the claim of infringement is caused by:

- SEB’s misuse or unauthorized modification of the Deliverables;

- SEB’s failure to use corrections or enhancements made freely available by Contractor;

- SEB’s use of the Deliverables in combination with any product or information not owned, recommended, or developed by Contractor;

- SEB’s distribution, marketing or use by third parties of the Deliverables; or

- Information, direction, specifications or materials provided by SEB or its contractors and not provided by Contractor’s written direction.

If any Deliverable is, or in Contractor’s opinion is likely to be, held to be infringing, Contractor shall at its expense and option either:

- Procure the right for SEB to continue using it,

- Replace it with a non-infringing equivalent,

- Modify it to make it non-infringing, or

- Direct the return of the Deliverable and refund to SEB the fees paid for the Deliverable less a reasonable amount for SEB’s use of the Deliverable up to the time of return.

The foregoing remedies constitute SEB’s sole and exclusive remedies and Contractor’s entire liability with respect to infringement.

## 28.  Intellectual Property Ownership

- Rights in Deliverables. Upon final payment, Contractor shall, subject to Section 28 (B) (Rights in Accenture Knowledge Capital) below and to any restrictions applicable to any third-party materials embodied in the Deliverables (including, but not limited to, Customizations and related documentation developed by Contractor hereunder), grants to SEB a perpetual, nontransferable, non-exclusive paid-up right and license to use, copy, modify and prepare derivative works of the Deliverables, for purposes of SEB’s internal business use relating exclusively to the operation and maintenance of SVRS. After acceptance of a Deliverable by the SEB, and pending final payment, Contractor hereby grants to SEB a revocable, nontransferable, non-exclusive unpaid right and license to use, copy, modify and prepare derivative works of such Deliverable for purposes of SEB’s internal business relating exclusively to the design, development, operation and maintenance of SVRS.  To the extent any Deliverable contains Contractor Confidential Information, it shall be subject to Section 40 (Confidentiality of Records) below.  All other intellectual property rights in the Deliverables remain in and/or are assigned to the Contractor.  The Parties shall cooperate with each other and execute such other documents as may be necessary or appropriate to achieve the objectives of this Section.

- Rights in Accenture Knowledge Capital.  The SEB shall have or obtain no rights in any Accenture Knowledge Capital other than (i) to use the same as authorized by Contractor in writing from time to time solely for purposes of performing SEB Responsibilities, (ii) to the extent the Accenture Knowledge Capital is incorporated into a Deliverable, to use it as part of the Deliverable for purposes of SEB’s internal business use relating exclusively to the operation and maintenance of SVRS, or (iii) pursuant to Contractor’s standard license for such Accenture Knowledge Capital or, in the case of Accenture Knowledge Capital owned by third parties, pursuant to terms acceptable to the applicable third party.  If any Accenture Knowledge Capital is made available to SEB under (i) above, it will be made available in an “AS IS” condition and without express or implied warranties of any kind; and any Accenture Knowledge Capital made available under (iii) above shall be subject only to applicable terms of the applicable license.  As between the SEB and the Contractor, Accenture Knowledge Capital will be deemed Confidential Information of the Contractor for purposes of Section 40 (Confidentiality of Records).

- Authorized User Access.  For purposes of this Section 28 (Intellectual Property Ownership), license rights in the Deliverables and Accenture Knowledge Capital shall extend to Authorized Users in the same manner and subject to the same restrictions as to SEB.  The SEB shall put all Authorized Users on notice as to the proprietary and/or confidential nature of the AESM Software, Customizations, Accenture Knowledge Capital, Deliverables, and other proprietary and/or confidential information or materials of Contractor.  Additionally, any Authorized User that is an agent, subcontractor or independent contractor (including SEB’s program management contractor hired by SEB for this project, but excluding officers and employees of the State of Wisconsin, Counties or Municipalities) must sign a confidentiality agreement, consistent with industry standard terms and conditions, with Contractor before such party is provided access to AESM Software, Customizations, Accenture Knowledge Capital, Deliverables, and other proprietary and/or confidential information or materials of Contractor.  If SEB becomes aware of any unauthorized use by Authorized Users of Contractor proprietary and/or confidential information or materials, SEB shall use its best efforts, at SEB’s expense, to promptly recover the information or property, and take all reasonable steps necessary to prevent its unauthorized use or further disclosure.

- Independent Development. In no event shall Contractor be precluded from independently developing for itself, or for others, anything, whether in tangible or non-tangible form, which is competitive with, or similar to, the Deliverables.  In addition, Contractor shall be free to use its general knowledge, skills and experience, and any ideas, concepts, know-how, and techniques that are acquired or used in the course of providing the Services.

## 29.  Rights in Data and Copyright – Federal Reserved Rights

As authorized by 41 C.F.R. 105-71.134, upon final payment and subject to Section 40 (Confidentiality of Records) herein, the federal government, through the SEB, reserves a royalty free, nonexclusive, and irrevocable license to reproduce, publish or otherwise use, subject to nondisclosure and internal use restrictions and Wisconsin State law, and to authorize the SEB and others to use, for Federal Government purposes:

- The copyright license in any Deliverables that are documents originally developed by Contractor under this Contract or a resulting subcontract; and,

- Any rights of copyright license in any Deliverables that are documents originally developed by Contractor under this Contract to which a contractor/grantee, or third-party subcontractor purchases ownership with federal assistance.

# 30.  Source Code Escrow

The Contractor shall maintain Source Code (including new releases of AESM Software provided during the performance of Warranty and Maintenance Services) in an Escrow Account for the benefit of the SEB with the U.S. Bank in Madison, Wisconsin acting as the Escrow Agent. The Source Code within the Escrow Account shall not include third party source code, except as the parties mutually agree in an amendment to this Contract.  The Source Code, in the form accepted by SEB at Release 2 Final Acceptance, shall be deposited into the Escrow Account within thirty (30) business days following the SEB’s Final Acceptance of Release 2 of the SVRS and each subsequent AESM Software release.  The SEB maintains the right to examine the Source Code in the Escrow Account for purposes of verifying the Source Code meets the Release 2 Final Acceptance criteria.  All costs for the Escrow Account shall be borne by the SEB and Contractor’s obligations under this Section 30 (Source Code Escrow) are subject to SEB’s payment of all costs due to maintain the Escrow Account.  In the event that the Contractor fails to maintain the Source Code in the Escrow Account within thirty (30) business days after Release 2 Final Acceptance and each subsequent AESM Software release, SEB may, at its option, assess daily Liquidated Damages of one thousand dollars ($1,000) from the thirty-first (31) business day after Final Acceptance of Release 2 until the current and correct Source Code is deposited in the Escrow Account, not to exceed sixty (60) business days.

In the event that the Contractor ceases to support and maintain AESM Software and the SEB has not breached any term or condition of this Contract (including the AESM Software License Agreement), the SEB shall have the right to access and utilize the Source Code deposited in the Escrow Account strictly for purposes of maintaining and operating SVRS for the State of Wisconsin, subject to licensing, confidentiality and other terms and conditions of this Contract.

The SEB will be responsible for setting up the Escrow Account agreement with the U.S. Bank in Madison, Wisconsin and all associated Escrow Account costs.  The SEB shall ensure that the Escrow Account agreement provides necessary access rights to allow the Contractor to perform its obligations under this Section 30 (Source Code Escrow).  The Contractor shall designate the SEB as a beneficiary in a Master Source Code Escrow Agreement.  The Contractor shall not amend or terminate the Master Source Code Escrow Agreement without the express written consent of the SEB, which shall not be unreasonably withheld, conditioned or delayed.  The Contractor shall give written notice to the SEB within ten (10) calendar days of each Source Code deposit.

The Source Code shall not intentionally contain any expiry key or other mechanism for establishing a date or time beyond which the software license will be invalid or beyond which the SVRS Application will not function in accordance with Specifications.

Default by the Contractor shall be deemed to have occurred under this Section 30 (Source Code Escrow) upon occurrence of any of the following:

- If Contractor has availed itself of, or been subjected to by any third-party, a proceeding in bankruptcy in which Contractor is the named debtor; an assignment by Contractor for the benefit of its creditors; the appointment of a receiver for Contractor; or any other proceeding involving insolvency or the protection of, or from, creditors and same has not been discharged or terminated without any prejudice to SEB rights or interest under this License agreement within thirty (30) calendar days.

- If Contractor has ceased its on-going business operations, or the sale, licensing, maintenance, and support of the AESM Software to the marketplace.

- If the Contractor materially breaches or defaults any term or condition of the Contract and does not cure such breach or default pursuant to Section 31 (Termination for Cause / Default), and the SEB terminates the Contract.

## 31.  Termination for Cause / Default

- Contractor Failure.  If Contractor refuses or fails to perform any of the provisions of this Contract that rise to a level of a material breach in a diligent and a timely manner:

- SEB shall notify Contractor in writing of the non-performance identifying the basis for such notice, and shall request prompt performance in accordance with the terms and conditions of this Contract. SEB may, upon giving Contractor a sixty (60) calendar days written notice (or longer period as SEB may agree), terminate Contractor’s right to proceed with this Contract, in whole (but not in part), for Contractor’s material breach of a term or condition in this Contract unless the Contractor cures such breach within the sixty (60) calendar period.

In the event Contractor does not cure a material breach within the agreed to time period, upon the return of all Deliverables and Accenture Knowledge Capital from SEB to Contractor, Contractor shall pay SEB for all Services rendered, expenses incurred, and any other verifiable direct costs incurred by SEB resulting from the SEB’s termination of the Contract for cause, subject to the limitation of liability set forth in Section 37 (Limitation of Liability) of this Contract.

- Notwithstanding termination of the Contract, and subject to any reasonable directions from the other Party, both Parties shall take timely, reasonable, and necessary action to protect, preserve, and return property, including Confidential Information, in the custody and control of the a Party in which the other Party holds an interest.

- Subsequent to the SEB’s notice to terminate Contractor’s right to proceed, if the SEB determines that the Contractor’s failure to perform was excusable, and that the Contractor’s performance otherwise would have met the terms of this Contract, the Delivery Schedule in Exhibit B – Statement of Work) may be revised upon SEB’s approval subject to the rights of the SEB.  If, after notice of termination of the Contractor’s right to proceed under the provisions of this paragraph, the SEB determines that the Contractor was not in default or that the delay was excusable, the rights and obligations of the Parties shall be the same as if the notice of termination had been issued pursuant to the Termination for Convenience clause.

- In the event of an uncured breach by Contractor and subject to the terms and conditions of this Contract, including Sections 28 (Intellectual Property Ownership), 29 (Rights in Data and Copyright – Federal Reserved Rights) and 40 (Confidentiality of Records), Contractor shall make available to the SEB, subject to the terms in Section 30 (Source Code Escrow), all then-current Source Code.

- SEB shall pay Contractor for Services and Deliverables accepted up to the date of termination, and each Party shall promptly deliver to the other Party, or upon request, certify the status of, all data, materials and programs of the other Party (except as expressly provided herein) in connection with this Contract.  Payment to Contractor shall include payment for all Services rendered up to the last day Services are provided, including Transition Services (if any) but not unpaid Retainage.  If the Contract is terminated after Release 1 Final Acceptance, but prior to Release 2 Final Acceptance, SEB shall also pay the January 2006 and February 2006 Retainage payments. If the Contract is terminated after Release 2 Final Acceptance, SEB shall pay all Retainage.

  - SEB Failure.  If the SEB refuses or fails to perform any of the provisions of this Contract that rise to a level of a material breach in a diligent and timely manner:

- The Contractor shall notify the SEB in writing of the non-performance, and request prompt performance in accordance with the terms and conditions of this Contract.

- The Contractor may, upon giving the SEB a sixty (60) calendar days written notice (or longer period as Contractor may agree), terminate SEB’s right to proceed with this Contract, in whole (but not in part), for SEB’s breach of a material term or condition in this Contract unless the SEB cures such breach within the sixty (60) calendar period.

- The SEB shall pay the Contractor for all Services and Deliverables accepted up to the date of termination, in addition to a prorated portion of in-process Deliverables, associated Retainage and Demobilization Costs, and each Party shall promptly deliver to the other Party, or upon request, certify the status of, all data, materials and programs of the other Party (except as expressly provided herein) in connection with this Contract.  Payment to Contractor shall include payment for all Services rendered up to the last day Services are provided, including Transition Services (if any).

## 32.  Termination for Convenience

  - Termination.  The SEB may terminate the Contract in whole (but not in part), at any time, when the interests of the SEB so require.  The SEB shall give a minimum of sixty (60) calendar days written notice of termination under this clause to Contractor.  Exercise of the Termination for Convenience Clause does not imply a breach of this Contract by either Party, and SEB will so indicate this understanding in the termination notice.

  - Contractor’s Obligations.  The Contractor shall not incur any further obligations in connection with the terminated work after its receipt of termination notice, and on the date set in the notice of termination, the Contractor shall stop work as directed.  The Contractor also shall terminate outstanding orders and subcontracts related to the terminated work.  The Contractor shall settle the claims arising out of the termination of these outstanding orders and subcontracts and the SEB shall pay the Contractor for all such settlement claims.  The SEB may direct the Contractor in writing to assign the Contractor’s right, title, and interest under any terminated orders or subcontracts to the SEB, subject to the Contractor’s right to permit such assignment and at an additional cost (if any) that may be charged by the vendor or subcontractor upon such assignment.

  - Compensation.

- The Contractor shall submit a final invoice within ninety (90) days from the last day Services are performed (including Transition Services, if any) or longer period as the SEB may agree.

- The SEB shall pay the Contractor the amounts as follows:

- Contract prices for Services and Deliverables accepted under this Contract;

- All undisputed amounts or damages due the Contractor for Services rendered and expenses incurred (including all Deliverables accepted and a pro rata portion of Deliverables in-process, including associated Retainage) up to the date of termination, as well as any verifiable Demobilization Costs.  Demobilization Costs shall not exceed $30,000.

- Costs of settling and paying claims arising out of the termination of outstanding orders or subcontracts pursuant to the Contractor’s obligations paragraph of this clause.

- The reasonable settlement costs of the Contractor include accounting, legal, clerical, and other expenses reasonably necessary for the preparation of settlement claims.

- The settlement shall not exceed the total Contract Price, less payments previously made by SEB.

- All invoices billed and paid shall be in the currency of the United States of America.  The Parties agree that any pre-printed terms contained in the SEB’s purchase orders, acknowledgments, shipping instructions, or other forms or in Contractor’s invoices, that are inconsistent with or different from the terms of this Contract will be void and of no effect even if signed by the Party against which their enforcement is sought.  Costs claimed or agreed to under this Section shall be in accordance with applicable sections of the Wisconsin Statutes.

- In any event, the period during which such costs shall be computed shall not extend beyond the expiration date of the Contract and such costs shall not duplicate any payments made for completed Deliverables, nor exceed the amounts that would otherwise have been due had they been completed.

## 33.  Cancellation for Misappropriation / Nonappropriation

The SEB reserves the right to cancel this Contract in whole (but not in part), without penalty, due to Contractor’s misappropriation of funds, or in the event that the state or the federal government withdraws or fails to appropriate the funds necessary to complete this Contract.  The SEB shall provide reasonable advance notification in the event that funds are not appropriated, and the SEB shall not authorize work to be performed by Contractor if funds have not been appropriated.  Contractor has no obligation to perform any work, which exceeds funds appropriated.  Termination due to non-appropriation shall be considered a termination for SEB’s convenience in accordance with Section 32 (Termination for Convenience).

## 34.  Responsibilities Upon Termination or Cancellation

Upon cancellation or termination of this Contract for any reason:

- After termination of this Contract for any reason (except termination of this Contract by the Contractor for a SEB default), the SEB shall have the right to continue to use the Contractor-owned AESM Software subject to the SEB’s payment in full for all Services rendered and expenses incurred as described in Sections 31 (Termination for 
Cause / Default), 32 (Termination for Convenience), and 34 (Responsibilities Upon Termination or Cancellation) above, including payment in full to the Contractor as described herein and the SEB’s conformance to the terms and conditions of this Contract and the AESM Software License Agreement.

- The Contractor shall, if requested by the Contract Administrator at least sixty (60) calendar days prior to such termination and subject to a Change Order as Extra Work, provide reasonable training for the SEB and/or continued performance of the Services specified in the Contract for up to six (6) months, commencing with the date of termination.  The Contract shall be extended by the number of days training or continued Services are performed. For providing such training or continued service, after the term of the Contract, the SEB shall pay the Contractor at the hourly rates set forth in Exhibit A – Payment Schedule.

- Notwithstanding termination of the Contract, and subject to any reasonable directions from the other Party, both Parties shall take timely, reasonable, and necessary action to protect, preserve, and return property, including Confidential Information, in the custody and control of the a Party in which the other Party holds an interest. Each Party shall promptly deliver to the other Party, or upon request, certify the status of, all Confidential Information of the other party in its possession in connection with this Contract. SEB’s license rights to the Deliverables (including AESM Software) as set forth herein shall survive expiration or termination (except for Contractor’s Termination for Cause) of this Contract.

## 35.  Transition Services.

Upon cancellation or termination for any reason, the Contractor shall provide such reasonable cooperation, assistance and services, and will assist the SEB in the migration of the SEB’s production operations to the SEB’s control or to the control of an alternative contractor upon written notice to the Contractor at least twenty (20) business days prior to termination and subject to the terms and conditions set forth in Section 40 (Confidentiality of Records), Section 26 (Intellectual Property Licenses and Permits) and Section 28 (Intellectual Property Ownership) of this Contract.  The Contract shall be extended by the number of days training or continued Services are performed.  As Extra Work and pursuant to an Amendment to this Contract, the Contractor shall perform all Transition Services requested by the SEB for a period of up to sixty (60) business days at the Contractor’s hourly rates set forth in Exhibit A – Payment Schedule for such additional Services and subject to the operation of Section 23 (Amendment and Change Orders), to allow the SVRS to continue without interruption and to facilitate the orderly transition and migration of the operation and maintenance of SVRS to the SEB or its designee, subject to the terms and conditions set forth in Section 40 (Confidentiality of Records), and Section 26 (Intellectual Property Licenses and Permits) of this Contract.

## 36.  Liquidated Damages

The SEB declares, and the Contractor acknowledges, that the SEB may suffer damages due to the Contractor’s delay or lack of performance of the terms and conditions of the Contract.  Since it is impractical and difficult to fix actual damages sustained in the event of any such delay or nonperformance, the SEB and the Contractor agree that damages sustained from the following causes shall be the amount set forth in this Section as liquidated damages and not as a penalty.

At the SEB’s option, for the Contractor’s delays or lack of performance, the below described liquidated damages (“Liquidated Damages”) may be deducted by the SEB from any monies due and payable to the Contractor and any amount outstanding over and above the amounts deducted from invoices shall be promptly tendered by check by the Contractor to the SEB:

- Milestone VII Delivery Date Delay.  The Parties agree that the SEB may assess Contractor, beginning on the first business day after the Milestone VII “SVRS Release 1 Delivery for User Testing” Date, as set forth in Section 9 (Project Milestones), daily Liquidated Damages for each day the Contractor is late in delivering Milestone VII to SEB so that Milestone VII is available for User Acceptance Testing, in the amount of Three Thousand Dollars ($3,000) per calendar day, not to exceed a total of Ninety Thousand Dollars ($90,000).

- Key Personnel.  Key Personnel, as set forth in Section 16 (Key Personnel and Personnel Changes), diverted by the Contractor without the SEB written approval and that were diverted for reasons other than Key Personnel Replacement Exceptions, which are not on-site at least ten (10) business days prior to the departure date of the person being replaced, shall entitle the SEB to Liquidated Damages in the amount of One Thousand Dollars ($1,000) per business day until replacement, not to exceed a total of Twenty Thousand Dollars ($20,000).

- Source Code Escrow.  In the event that the Contractor fails to deposit or maintain a the Source Code in the Escrow Account after Final Acceptance of Release 2 as described in Section 30 (Source Code Escrow) herein, the SEB may assess Liquidated Damages in the amount of One Thousand Dollars ($1,000) per business day, not to exceed a total of Sixty Thousand Dollars ($60,000).

- Service Level Requirements.  Contractor’s failure to meet a Service Level Requirement as set forth in Attachment D- Service Level Agreement (each such failure defined as a “SLA Non-Conformity”) shall entitle the SEB to Liquidated Damages, as described below.  If two or more SLA Non-Conformities are occurring during the same period for different Service Level Metrics, the SEB may only assess the greater of the two or more SLA Non-Conformities (but may not assess more than one SLA Non-Conformity).  The Liquidated Damages for Non-Election Periods apply only to Non-Conformities that occur between 8:00 a.m. and 5:00 p.m. Central Time on regular business days.  The Liquidated Damages for an Election Period apply only to the hours 7:00 a.m. to 7:00 p.m. Central Time on regular business days.

| Service Level Metric Measurement Period | Election Period Remedy | Non-Election Period Remedy |
| --- | --- | --- |
| Application Performance | $1,500 a month when the number of transactions that exceed the Standard Time is more than 5% of all the transactions in that month. | $500 a month when the number of transactions that exceed the Standard Time is more than 5% of all the transactions in that month. |
| Help Desk Response Time | $1,000 a month when the number of Help Desk Calls with Response Times that exceed the Escalation Table Response Times is more than 5% of all Help Desk Calls for the month. | $250 a month when the number of Help Desk Calls with Response Times that exceed the Escalation Table Response Times is more than 5% of all Help Desk Calls for the month. |

Liquidated Damages General Conditions

The SEB shall notify the Contractor in writing of the assessment of liquidated damages or the potentiality of assessment of liquidated damages for any default specified herein within thirty (30) calendar days of the discovery of the occurrence.  If within the thirty (30) calendar days period after receipt of notice, Contractor believes the assessment of liquidated damages is inappropriate under the circumstances, Contractor may initiate the dispute resolution process as set forth in Section 69 (Dispute Resolution) of this Contract, in an attempt to resolve the matter to the mutual satisfaction of both parties.  The Contractor will have thirty (30) calendar days to either deduct the amount due from an invoice or to make payment via a check made out to the State of Wisconsin, except in the event the assessment of liquidated damages is in dispute, in which case no deduction nor payment of liquidated damages shall be due or payable except as finally determined after completion of the dispute resolution process.  The invoice deduction or the check payment must clearly indicate the amounts due and the dates of the assessments to be paid.

In the event of a dispute regarding the imposition or the amount of liquidated damages, the Contractor shall designate the Accenture eDemocracy Services President to discuss the dispute with the SEB’s Contract Administrator.

The Contractor shall not be liable for Liquidated Damages when delays arise out of a cause beyond the reasonable control and without the fault or negligence of the Contractor, including delays due to Force Majeure or due to the responsibility of the SEB, its agents, subcontractors, or third parties.

The assessment of Liquidated Damages shall be the sole and exclusive remedy for the particular breach event and are in lieu of other remedies (without limiting termination rights). SEB will not withhold payment due Contractor or other State obligations in addition to assessing Liquidated Damages. Any Liquidated Damages assessed shall reduce Contractor's limitation of liability cap set forth in Section 37 (Limitation of Liability) to the extent assessed.

The Contractor shall not be liable for Liquidated Damages for delays caused by the default of Contractor’s subcontractor, when such default arises out of a cause beyond the control of both Contractor and its subcontractor and without the fault or negligence of either of them.

# 37.  Limitation of Liability

- Contractor’s Liability.  The Contractor’s sole liability (whether in contract, tort, negligence, strict liability in tort or by statute or otherwise) for any claim in any manner related to this Contract, shall be the payment of direct damages and such damages shall in no event in the aggregate exceed:

- for any and all claims relating to the Implementation Services and the Warranty Services, One Hundred and Fifty percent (150%) of the fees received by Contractor for Implementation Services and Warranty Services as set forth in Section 3 (Contract Price) of this Contract, with respect to the work involved, and

- for any and all claims relating to the Maintenance Services and the Support Services, the fees received by Contractor during the four (4) month period directly preceding the claim, with respect to the work involved.

In no event shall either party be liable for any consequential, incidental, indirect, special or punitive damage, loss or expenses (including but not limited to business interruption, lost business, lost profits, or lost savings) even if it has been advised of their possible existence.  Any action by either party must be brought within two (2) years after the cause of action arose.

The allocations of liability in this Section 37 (Limitation of Liability) represent the agreed and bargained-for understanding of the parties and Contractor’s compensation for the Services reflects such allocations.

- No Liability for Certain Damages.  The Contractor shall not be liable to the SEB for any damages or claims to the extent such damages or claims were caused by the failure of the SEB or its agents or subcontractors to perform as required under this Contract, provided the Contractor has documentation or other tangible evidence of SEB’s failure to perform.

- Exclusions from Limitation; Survival.  The foregoing limitations do not apply to, and do not limit, any liability with respect to indemnification obligations set forth in Section 38 (Indemnification) of this Contract.

- SEB Rights.  The SEB may sue for breach of contract under all applicable legal theories.  The SEB’s damages for breach of contract shall be limited to the liability cap set forth in this Section 37 (Limitation of Liability).

## 38.  Indemnification

The Contractor shall indemnify, defend, and hold harmless the SEB and the State of Wisconsin, and its agents and employees from and against all third-party suits, claims, damages, judgments, losses and expenses, including attorneys' fees, relating to bodily injury or death of any person or damage to real and/or tangible personal property directly caused by the negligence or willful misconduct of Contractor, its subcontractors, or personnel during the course of the Services under this Contract. To receive this indemnity, SEB must promptly notify Contractor in writing of a claim or suit and provide reasonable cooperation and full authority to defend or settle the claim or suit.  Contractor shall have no obligation to indemnify SEB and the State of Wisconsin under any settlement made without Contractor’s written consent.

## 39.  General Legal Relations

The Contractor shall at all times comply with and observe all federal and State laws, local laws, ordinances, and regulations that are in effect during the period of the Contract and applicable to Contractor’s business.  It is understood by the parties that the Services do not include the provision of legal services or law interpretation of any kind.  The SEB shall remain responsible for complying with all federal and State laws, local laws, ordinances, and regulations relating to its operation and use of the Deliverables and SVRS. In carrying out any provisions of the Contract or in exercising any power or authority granted to the Contractor thereby, there shall be no personal liability upon the SEB, it being understood that in such matters the SEB acts as agent and representative of the State of Wisconsin.

While the Contractor will provide its Services and Deliverables as set forth herein to assist the SEB in the design, implementation, maintenance and support of the SVRS that meets the business requirements addressed by the federal Help America Vote Act of 2002 (HAVA), as mutually agreed to under the Specifications, the Contractor makes and the SEB receives no warranties or representations that the Services, Deliverables, SVRS Application or the SVRS will necessarily meet any third party’s (including the Federal government) interpretation of HAVA compliance as the law is currently defined or as it may change in the future.  Further, any law change (including HAVA-related law changes) that requires a change to the Scope of Services, Specifications or Deliverables, will be addressed as an amendment pursuant to Section 23 (Amendments and Change Orders) of this Contract.

# 40.  Confidentiality of Records

The Parties acknowledge that some of the data and information they may become privy to in the performance of the Contract through access by the other Party is of a confidential nature and each Party shall make all reasonable efforts so that it, its employees, and agents disseminate no such confidential information outside the purposes of this Contract.

Each Party (including Authorized Users, agents, and personnel of a party) shall observe confidentiality with respect to all aspects of any confidential information, proprietary data and/or trade secrets and any parts thereof, received by the other party in performance of the Services under this Contract.  Each Party agrees to protect the confidentiality of the other Party’s confidential information in the same manner that it protects the confidentiality of its own proprietary and confidential information of like kind, but in no event shall the receiving Party exercise less than reasonable care in protecting such confidential information. Nothing in this Contract shall prohibit or limit a receiving Party’s use of information (including, but not limited to, ideas, concepts, know-how, techniques, and methodologies):

- previously known to it without an obligation of confidence,

- independently developed by or for it,

- acquired by it from a third-party which is not, to its knowledge, under an obligation of confidence with respect to such information, or

- is or becomes publicly available through no breach of this Contract.

The restrictions herein shall survive the termination of the Contract for any reason and shall continue in full force and effect and shall be binding upon the receiving Party and its agents, employees, successors, assigns, subcontractors, or any party claiming an interest in the Contract on behalf of or under the rights of both Parties following any termination.  Both Parties shall advise all their agents, employees, successors, assigns and subcontractors that may be provided access to the confidential information of the other Party of the restrictions, present and continuing, set forth herein.

Nothing herein is intended or shall operate as a waiver of any applicable law governing disclosure of records, including subchapters II and IV, Chapter 19, Wisconsin Statutes.

## 41.  Payment Requirements and Invoicing

The SEB shall pay the Contractor’s Invoice as each Milestone is Acceptance Tested and has been accepted in writing by the SEB.  The SEB shall pay invoices properly submitted by the Contractor within thirty (30) days of receipt, providing that all Deliverables associated with the invoice have been delivered, installed (if required), and accepted as specified in the appropriate Milestone.  Any invoice remaining unpaid for more than thirty (30) days from receipt shall accrue interest at a rate of one (1%) percent per month pursuant to Section 16.528(2) of the Wisconsin Statutes.  Itemized invoices presented for payment must be submitted in accordance with instructions contained on the purchase order including reference to purchase order number and submittal to the correct address for processing.  Payments for support services costs and maintenance services costs, if any, shall be paid in the Fiscal Year when the Services are performed.

A good faith dispute shall create an exception to prompt payment.

## 42.  Progress Reports

The Contractor shall submit at least a monthly progress report to the SEB Contract Administrator during the Implementation Period.  The Contract Administrators shall reasonably determine the content, format and frequency of the progress reports.  The progress report shall at least describe the status of Contractor's performance since the preceding report, including all Deliverables accepted and the progress expected to be made in the next succeeding period.  Each report shall describe Contractor's activities and provide the status of each item on the schedule of Deliverables and Milestones in Exhibit B – Statement of Work.

## 43.  Recordkeeping and Record Retention

The Contractor shall establish and maintain adequate records of all expenditures incurred under the Contract.  All records shall be kept in accordance with generally accepted accounting procedures.  All procedures shall be in accordance with federal, state and local ordinances.

Upon a minimum twenty (20) business days’ prior written notice, the SEB shall have the right to audit, review, examine, copy, and transcribe within Contractor’s office during normal business any pertinent records or documents relating to the Contract held by the Contractor.  The Contractor shall retain all documents applicable to the Contract for a period of not less than three (3) years after final payment is made.

## 44.  Audits

Upon at least twenty (20) business days’ prior written notice by either Contractor or SEB to the other Party, the Party receiving such request shall provide the other (which may include its auditors and inspectors), with reasonable access to the records maintained by the other Party relating to this Contract subject to Section 43 (Recordkeeping and Record Retention) above.  The State of Wisconsin shall also have authority to perform an audit or audits.

Specifically excluded from such audit rights is any access to the following:

- Contractor's financial records unrelated to this Contract, Contractor’s internal cost data relating to this Contract, or otherwise unnecessary for the audit,

- Documents created by and for SEB or other communications related thereto that are confidential attorney work product or subject to attorney-agency privilege (“Privileged Work Product”), and

- Information that is unrelated to this Contract.

No Party shall be responsible for any taxes or any other liabilities imposed upon any other Party as a result of such audits and inspections.  Both Parties shall use reasonable efforts to minimize the number and duration of such audits or inspections conducted and to conduct such audits and inspections in a manner that will minimize the disruption to the other Party's business operations. The Party requesting an audit shall be responsible for the costs associated with the audit review. Information disclosed during any such audit shall be Confidential Information for purposes of this Contract and shall be shared in accordance with Section 40 (Confidentiality of Records) of this Contract.

This Section 44 (Audits) shall survive the termination of this Contract.

## 45.  SEB Furnished Property

- Provision of Property.  The SEB shall provide to the Contractor, for use in connection with and under the terms of this Contract, the SEB-furnished property described in Exhibit B – Statement of Work, together with any related data and information that the Contractor may request and is reasonably required for the intended use of the property (hereinafter referred to as “SEB-furnished property”).

- Unsuitable Property.  If SEB-furnished property is received by the Contractor in a condition not suitable for the intended use, the Contractor shall, upon receipt of it, notify the SEB, detailing the facts, and upon mutual agreement at SEB expense, either repair, modify, or return the property.

- Damage.  If damage occurs to SEB property before delivery to Contractor, the risk of which has been assumed by the SEB under this Contract, the SEB shall replace the items at the SEB’s expense.

- Access.  The SEB and its designees shall have access at reasonable times and upon advance written notice to the premises in which any SEB property is located for the purpose of inspecting the SEB property.  The Contractor shall maintain an inventory and accountability system acceptable to the SEB.

- Risk of loss.  Unless otherwise provided in this Contract, Contractor assumes the risk of, and shall be responsible for, any loss or destruction of, or damage to, SEB property that Contractor has received in its sole custody and care.  However, the Contractor is not responsible for reasonable wear and tear to SEB property or for SEB property properly consumed in performing this Contract.

## 46.  Security Clearance Background Checks

During the performance of the Services, the Contractor Project personnel will likely gain access to certain personally identifiable information deemed confidential (e.g., social security numbers), which shall be treated by Contract Project personnel in accordance with the terms and conditions of Section 40 (Confidentiality of Records).  Therefore, the Contractor shall, subject to the laws of the State of Wisconsin, have performed background security checks on Contractor Project personnel consistent with its standard corporate policies and procedures regarding background security checks (e.g., social security verification, educational background, credit report, felony and misdemeanor at all residential and school addresses five years prior to hire, U.S. national criminal file search, OFAC terrorist check).  The Contractor will not provide to the Project any Contractor personnel that do not satisfactorily pass its policies and procedures regarding background security checks, and the Contractor shall replace, pursuant to Section 16 (Key Personnel and Personnel Changes), any Contractor Project personnel that the Contractor may later become aware no longer satisfy such policies and procedures.

# GENERAL PROVISIONS

## 47.  Access to Facilities

Unless otherwise agreed to by the Parties, any and all access by the Contractor's employees to the facilities of the SEB shall be during normal State office hours and all Contractor employees shall be subject to the State site's security procedures which shall be provided to the Contractor in writing prior to such required access.  The SEB, State representatives and contractors shall not unreasonable delay or obstruct access by the Contractor to State facilities.

## 48.  Antitrust Assignment

The Contractor and the SEB recognize that in actual economic practice, overcharges resulting from antitrust violations are in fact usually borne by the SEB.  Therefore, the Contractor hereby assigns to the SEB any and all claims for such overcharges as to goods, materials or Services purchased in connection with the Contract.

## 49.  Applicable Law

The Contract shall be governed under the laws of the State of Wisconsin.  The Contractor shall at all times comply with and observe all federal and state laws, local laws, ordinances, and regulations that are in effect during the period of the Contract and applicable to the operation of its business. SEB shall at all times comply with and observe all federal and state laws, local laws, ordinances, and regulations that are in effect during the period of the Contract applicable to its use and operation of the Deliverables and the SVRS System. The SEB reserves the right to cancel any Contract with a federally debarred Contractor or a Contractor that is presently identified on the list of parties excluded from federal procurement and non-procurement contracts.

## 50.  Assignment

No right or duty in whole or in part of the Contractor under the Contract may be assigned or delegated without the prior written consent of the SEB.

## 51.  Conflict of Interest

The conflict of interest provisions of Chapters 180 and 181 of the Wisconsin Statutes shall apply to the Contractor under this Contract.

## 52.  Consent To Breach Not Waiver

The waiver by the SEB of any breach of any provision contained in the Contract shall not be deemed to be a waiver of such provision on any subsequent breach of the same or any other provision contained in the Contract.  Likewise, such a waiver shall not establish a course of performance between the Parties contradictory to the terms of the Contract.

## 53.  Contract Interpretation

The following rules of interpretation shall be applied in interpreting this Contract:

- headings and captions are for convenience only and are not to be used in the interpretation of this Contract;

- all references to Sections and Exhibits are to Sections or Exhibits to this Contract;

- as used in this Contract, the term “including” will always be deemed to mean “including without limitation”;

- consents or approvals required to be given under this Contract shall not be unreasonably withheld, delayed or denied unless the Contract expressly states otherwise; and

- all requests under this Contract shall be reasonable.

## 54.  Cooperation with Other Contractors or Subcontractors

The Contractor shall fully cooperate with any third-party contractor the SEB may engage to perform additional work under the Contract as reasonably required, which do not delay the Contractor from its delivery obligations and subject to confidentiality requirements set forth in this Contract.  The Contractor shall not intentionally commit any act that interferes with the performance of work by any other contractor or by the SEB.  The Contractor shall cooperate as reasonably required with the SEB and any other state agency working with the SEB, hardware manufacture representatives, system software suppliers, and communications systems suppliers in its performance of the Services.  The Contractor shall notify the SEB as soon as reasonably possible if it becomes aware of an act or omission of an SEB contractor that will delay or otherwise impair the provision of Services under this Contract however Contractor shall not be liable for the acts or omissions of any SEB contractor for any reason.  SEB shall be responsible for managing and supervising the SEB contractors and for any failure of the SEB contractors to comply with the SEB’s applicable obligations under this Contract.

If the work performed by any SEB contractor affects the Services being performed by the Contractor under this Contract or the SEB contractor otherwise uses resources furnished by the Contractor, the SEB shall use commercially reasonable efforts to ensure that such SEB contractor:

- cooperates with Contractor;

- follows reasonable Contractor standards, methodologies and procedures (including confidentiality and security procedures);

- complies with the license and confidentiality requirements of Contractor or vendors of the software on which such SEB’s Contractor is performing work; and

- executes, delivers and complies with any customary confidentiality and non-disclosure agreements reasonably required by Contractor of such vendors.

## 55.  Disclosure

The SEB may terminate this Contract for cause pursuant to Section 31 (Termination for Cause / Default) if a state public official, as defined in Section 19.42 of the Wisconsin Statutes, a member of a state public official's immediate family, or any organization in which a State public official or a member of the official's immediate family owns or controls a ten percent (10%) interest, is a party to the Contract, unless appropriate disclosure is made as required under Section 19.45 (6) of the Wisconsin Statutes, before the Contract is executed.  This disclosure must be made to the State of Wisconsin Ethics Board, 44 East Mifflin Street, Suite 601, Madison, Wisconsin 53703 (Telephone 608-266-8123).

## 56.  Force Majeure

If the Contractor is prevented from performing any of its obligations in whole or in part under the Contract as a result of an act of God, war, civil disturbance, disease, terrorism or the public enemy; riot, civil commotion or sabotage; expropriation, condemnation of facilities, changes in law, national or state emergencies or other governmental action; strikes, lockouts, work stoppages or other such labor difficulties; floods, droughts or other severe weather; fires, explosions or other catastrophes; or accidents causing damage to or destruction, in whole or in part, of the equipment or property necessary to perform the Services; or any other cause beyond its control, then such nonperformance shall not be grounds for the assessment of termination for cause, Liquidated Damages or any other remedy.  As soon as reasonably possible upon the occurrence of any such event, the Contractor shall commence to use reasonable efforts to limit the impact of such event at SEB’s expense.  This Section 56 (Force Majeure) shall not be construed as relieving the Contractor of its responsibility for any of its obligations, or for any obligation being performed by a subcontractor or supplier of Services, unless the subcontractor or supplier was prevented from performing such obligation by one of the events set forth above.

## 57.  Kickbacks

The Contractor certifies and warrants that no gratuities, kickbacks or contingency fees were paid in connection with the Contract, nor were any fees, commissions, gifts, or other considerations made contingent upon the award of this Contract.  If the Contractor breaches or violates this warranty, the SEB may, at its discretion, terminate this Contract without liability to the SEB, or deduct from the Contract price or consideration, or otherwise recover, the full amount of any commission, percentage, brokerage, or contingency fee.

## 58.  Minority Business Subcontractors

The State of Wisconsin is committed to the promotion of minority business in the State's purchasing program and a goal of placing 5% of its total purchasing dollars with certified minority businesses.  Authority for this program is found in Sections 15.107(2), 16.75(4), 16.75(5) and 560.036(2) of the Wisconsin Statutes.  The SEB is committed to the promotion of minority business in the State's purchasing program.

The State of Wisconsin policy provides that minority-owned business enterprises certified by the Wisconsin Department of Commerce, Bureau of Minority Business Development should have the maximum opportunity to participate in the performance of its Contracts.  The Contractor is strongly urged to use due diligence to further this policy by awarding subcontracts to minority-owned business enterprises or by using such enterprises to provide goods and services incidental to this Contract, with a goal of awarding at least 5% of the Contract price to such enterprises.

The Contractor shall furnish appropriate quarterly reports about its effort to achieve this goal, including the identities of such enterprises certified by the Wisconsin Department of Commerce and their Contract amount.  The SEB will provide the format for the reporting.

A listing of certified minority businesses, as well as the services and commodities they provide, is available from the Department of Administration, Office of the Minority Business Program, 608/267-7806.  The listing is published on the Internet at: http://www.doa.state.wi.us/dsas/mbe/index/asp.

## 59.  Nondiscrimination / Affirmative Action

The Contractor shall not to discriminate against any employee or applicant for employment because of age, race, religion, color, handicap, sex, physical condition, developmental disability as defined in Section 51.01(5) of the Wisconsin Statutes, sexual orientation as defined in Section 111.32(13m) of the Wisconsin Statutes, or national origin.  This provision shall include, but not be limited to, employment, upgrading, demotion or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship.  Except with respect to sexual orientation, the Contractor shall also take affirmative action to ensure equal employment opportunities.

Contracts estimated to be over twenty-five thousand dollars ($25,000) require the submission of a written affirmative action plan by the Contractor.  An exemption occurs from this requirement if the Contractor has a workforce of less than twenty-five (25) employees.  Within fifteen (15) working days after the Contract is awarded, the Contractor must submit the plan to the SEB for approval.  Instructions on preparing the plan and technical assistance regarding this clause are available from the SEB.

The Contractor shall post in conspicuous places, available for employees and applicants for employment, a notice to be provided by the SEB that sets forth the provisions of the SEB's nondiscrimination law.

Failure to comply with the conditions of this clause may result in the Contractor being declared an "ineligible" contractor, cancellation of the Contract, or withholding of payment.

## 60.  Material Safety Data Sheet

If any item(s) on an order(s) resulting from this award(s) is a hazardous chemical, as defined under 29CFR 1910.1200, the Contractor shall provide one (1) copy of a Material Safety Data Sheet for each item with the shipped container(s) and one (1) copy with the invoice(s).

## 61.  No Finder’s Fee

No finder’s fee, employment agency fee, or other such fee related to the procurement of this Contract shall be paid by either party.

## 62.  Promotional Advertising / News Releases

Reference to or use of the State of Wisconsin, any of its departments, agencies or other subunits, or any State official or employee for commercial promotion is prohibited.  News releases pertaining to the Contract shall not be made without prior approval of the SEB.  Release of broadcast e-mails pertaining to the Contract shall not be made without prior written authorization of the SEB.  Notwithstanding the above, the Contractor may, without the SEB’s prior consent, publicize the general nature and existence of the Project and the Contract to the extent it is not a breach of the SEB’s confidential information.

## 63.  Safety Requirements

All materials, equipment, and supplies provided to the SEB must comply fully with all safety requirements as set forth by the Wisconsin Administrative Code, the Rules of the Industrial Commission on Safety, and all applicable OSHA Standards.

## 64.  Severability

If any provision of the Contract is declared or found to be illegal, unenforceable, or void, then both Parties shall be relieved of all obligations under that provision. Performance under the remaining terms of the Contract shall continue.

## 65.  Site Rules and Regulations

The Contractor’s employees and agents, while on the SEB's premises or in the presence of SEB employees, shall comply with the SEB's work rules and regulations applicable to the work site.

Neither party shall require waivers or releases of any personal rights from representatives of the other in connection with visits to its premises.  Both Parties agree that they shall plead no such releases or waivers in any action or proceeding.

## 66.  Contractor Tax Delinquency

If the Contractor has a delinquent Wisconsin tax liability the SEB may offset payments due under the Contract.

## 67.  Taxes

The State of Wisconsin and its agencies are exempt from payment of all federal tax and Wisconsin state and local taxes on its purchases except Wisconsin excise taxes as described below.

The State of Wisconsin, including all its agencies, is required to pay the Wisconsin excise or occupation tax on its purchase of beer, liquor, wine, cigarettes, tobacco products, motor vehicle fuel and general aviation fuel.  However, it is exempt from payment of Wisconsin sales or use tax on its purchases.

68.  Third Party Beneficiaries

The Parties acknowledge that they are entering into this Contract solely on the basis of the agreements and representations contained herein, and that they have not relied upon any representations, warranties, promises, or inducements of any kind, whether oral or written, and from any source, other than those that are expressly contained within this Contract.

69.  Dispute Resolution

The parties agree that, in the event of a dispute or alleged breach subject to Section 31 (Termination for Cause / Default) of this Contract, they will work together in good faith first, to resolve the matter internally by escalating it to higher levels of management and, then if necessary, to use a mutually agreed alternative dispute resolution technique prior to resorting to litigation.  In the event the parties fail to mutually agree upon such technique within thirty (30) days after good faith attempts at internal resolution have failed, either party may resort to litigation. This provision shall not apply to disputes involving confidentiality or infringement of intellectual property rights (in which case either party shall be free to seek available remedies in any forum).

Signatures

Wisconsin State Elections Board

For the State of Wisconsin	Accenture LLP

| ___________________________________ | ___________________________________ |
| --- | --- |

Kevin J. Kennedy	Meg. T. McLaughlin

Executive Director	President

State Elections Board	Accenture eDemocracy Services

| ___________________________________ | ___________________________________ |
| --- | --- |

Date			Date